## Estimasi Transportation
NO | PO NUMBER | DUID | REGION | PIC PICK UP | SUB REGION | SOW | STATUS MATERIAL | Jarak Trip | ITEM PO | ITEM PO DESCRIPTION | Trip | Price Estimation | Quantity | PO Amount | WCC 100% | PAYMENT | Date | REMARKS
1 | S1ID2025060419WBF1-5 | NACH_0010_NACH_0008 | North Sumatra | ADIONO | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 622KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-30 | Done
2 | S1ID2025060419WBF1-5 | NMDN_0021_ZMDN_4024 | North Sumatra | ADIONO | North Sumatra | Dismantle MW Keep | INBOUND DONE | 62.6KM | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 1 | 1000000 | Done | 1000000 | 2025-10-27 | Done
3 | S1ID2025060419WBF1-5 | NACH_0034_NACH_0008 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 625KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-27 | Done
4 | S1ID2025060419WBF1-5 | NACH_0044_NACH_0043 | North Sumatra | ADIONO | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 350 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-27 | Done
5 | S1ID2025060419WBF1-5 | ZMDN_5415_ZMDN_4017 | North Sumatra | ADIONO | North Sumatra | Dismantle MW Keep | INBOUND DONE | 48KM | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-30 | Done
6 | S1ID2025060419WBF1-5 | NACH_0059_NACH_0009 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 624KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-27 | Done
7 | S1ID2025060419WBF1-5 | NACH_0071_NACH_0061 | North Sumatra | ADIONO | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 322KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-27 | Done
8 | S1ID2025060419WBF1-5 | NACH_0124_NACH_0003 | North Sumatra | TEAM EXTERNAL | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 621KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-27 | Done
9 | S1ID2025060419WBF1-5 | ZMDN_4656_ZMDN_4015 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 257KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-27 | Done
10 | S1ID2025060419WBF1-5 | ZMDN_4838_ZMDN_4015 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 256KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-27 | Done
11 | S1ID2025060419WBF1-12 | ZMDN_5339_NMDN_0787 | North Sumatra | ADIONO | North Sumatra | Dismantle MW Keep | INBOUND DONE | 265KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
12 | S1ID2025060419WBF1-5 | NMDN_0073_NMDN_0195 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 254KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-27 | Done
13 | S1ID2025060419WBF1-12 | ZMDN_5372_ZMDN_4712 | North Sumatra | ADIONO | North Sumatra | Dismantle MW Keep | INBOUND DONE | 215KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
14 | S1ID2025060419WBF1-12 | SUM-SU-AKK-2441_SUM-SU-AKK-1149 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 238KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
15 | S1ID2025060419WBF1-12 | SUM-SU-AKK-1527_SUM-SU-AKK-1137 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 255KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
16 | S1ID2025060419WBF1-5 | ZMDN_4624_ZMDN_5379 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 303KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-27 | Done
17 | S1ID2025060419WBF1-12 | SUM-SU-AKK-2412_SUM-SU-AKK-1137 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 268KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
18 | S1ID2025060419WBF1-12 | SUM-SU-KIS-1802_SUM-SU-KIS-0139 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 185KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
19 | S1ID2025060419WBF1-14 | NMDN_0075_SUM-SU-AKK-0163 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 254KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
20 | S1ID2025060419WBF1-14 | ZMDN_5404_SUM-SU-PSP-1500 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 374KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
21 | S1ID2025060419WBF1-12 | ZMDN_4720_NMDN_0167 | North Sumatra | TEAM EXTERNAL | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 255KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
22 | S1ID2025060419WBF1-12 | SUM-SU-KPI-2426_SUM-SU-KPI-1163 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 363KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
23 | S1ID2025060419WBF1-14 | NACH_0093_SUM-AC-BNA-0043 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 623KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km | 1 Trip | 1000000 | 1 Trip | 1000000 | Done | 1000000 | 2026-04-21 | Done
24 | S1ID2025060419WBF1-12 | NACH_0022_NACH_0135 | North Sumatra | ADIONO | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 625KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
25 | S1ID2025060419WBF1-12 | NACH_0053_NACH_0055 | North Sumatra | ADIONO | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 516KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
26 | S1ID2025060419WBF1-5 | SUM-SU-AKK-1510_SUM-SU-AKK-1130 | North Sumatra | VALDINO RAWUNG | North Sumatra | Dismantle MW Keep | INBOUND DONE | 263 KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-27 | Done
27 | S1ID2025060419WBF1-12 | SUM-SU-AKK-1517_SUM-SU-AKK-1129 | North Sumatra | VALDINO RAWUNG | North Sumatra | Dismantle MW Keep | INBOUND DONE | 288 KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
28 | S1ID2025060419WBF1-12 | SUM-SU-KPI-2543_SUM-SU-KPI-1170 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 326 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
29 | S1ID2025060419WBF1-5 | NMDN_0847_NMDN_0040 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 179KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-10-30 | Done
30 | S1ID2025060419WBF1-7 | ZMDN_5382_NMDN_0840 | North Sumatra | ADIONO | North Sumatra | Dismantle MW Keep | INBOUND DONE | 141KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
31 | S1ID2025060419WBF1-7 | NMDN_0809_NMDN_0180 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 215KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
32 | S1ID2025060419WBF1-7 | NMDN_0854_NMDN_0086 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 254KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
33 | S1ID2025060419WBF1-14 | NMDN_0975_ZMDN_4213 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 265KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
34 | S1ID2025060419WBF1-14 | NMDN_0977_NMDN_0486 | North Sumatra | TEAM EXTERNAL | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 246KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
35 | S1ID2025060419WBF1-14 | NMDN_0978_NMDN_0179 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 235KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
36 | S1ID2025060419WBF1-7 | ZMDN_4740_NMDN_0461 | North Sumatra | ADIONO | North Sumatra | Dismantle MW Keep | INBOUND DONE | 160KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
37 | S1ID2025060419WBF1-14 | ZMDN_4973_SUM-SU-BLG-1677 | North Sumatra | ADIONO | North Sumatra | Dismantle MW Keep | INBOUND DONE | 207KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
38 | S1ID2025060419WBF1-7 | SUM-SU-BLG-0029_SUM-SU-BLG-1745 | North Sumatra | ADIONO | North Sumatra | Dismantle MW Keep | INBOUND DONE | 207KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
39 | S1ID2025060419WBF1-7 | SUM-AC-JTH-0549_SUM-AC-SAB-0473 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 591KM | 350000266071 | Transportation service between Medan WH and Kota Sabang,Truck | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2025-11-18 | Done
40 | S1ID2025060419WBF1-14 | NMDN_0959_SUM-SU-AKK-1131 | North Sumatra | TEAM EXTERNAL | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 256 KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
41 | S1ID2025060419WBF1-7 | SUM-SU-KPI-2428_SUM-SU-KPI-1151 | North Sumatra | TEAM EXTERNAL | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2025-11-18 | Done
42 | S1ID2025060419WBF1-7 | ZMDN_5412_NMDN_0530 | North Sumatra | TEAM EXTERNAL | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
43 | S1ID2025060419WBF1-7 | NMDN_0119_NMDN_0167 | North Sumatra | TEAM EXTERNAL | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
44 | S1ID2025060419WBF1-7 | NMDN_0882_NMDN_0167 | North Sumatra | TEAM EXTERNAL | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
45 | S1ID2025060419WBF1-4 | SUM-AC-BIR-0593_SUM-AC-BIR-0271 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Reroute 2+0 | OUTBOUND DONE | 387KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-12-16 | Done
46 | S1ID2025060419WBF1-8 | SUM-AC-BIR-0011_SUM-AC-BIR-0352 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Reroute 2+0 | OUTBOUND DONE | 403KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
47 | S1ID2025060419WBF1-1 | SUM-AC-LSK-0105_SUM-AC-LSK-0146 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Swap Upgrade 2+0 | OUTBOUND DONE | 281KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-09-24 | Done
48 | S1ID2025060419WBF1-1 | SUM-AC-MRN-0527_SUM-AC-BIR-0002 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Swap Upgrade 2+0 | OUTBOUND DONE | 488KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-09-24 | Done
49 | S1ID2025060419WBF1-1 | ZMDN_4740_SUM-SU-SDK-1235 | North Sumatra | ADIONO | North Sumatra | Reroute 2+0 | OUTBOUND DONE | 149KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-09-24 | Done
50 | S1ID2025060419WBF1-4 | SUM-AC-SGI-0177_SUM-AC-SGI-0182 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Swap Upgrade 2+0 | OUTBOUND DONE | 499KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-12-16 | Done
51 | S1ID2025060419WBF1-4 | SUM-AC-SGI-0273_SUM-AC-SGI-0181 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Swap Upgrade 2+0 | OUTBOUND DONE | 509KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-12-16 | Done
52 | S1ID2025060419WBF1-4 | SUM-AC-SGI-0274_SUM-AC-SGI-0181 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Swap Upgrade 2+0 | OUTBOUND DONE | 514KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2025-12-16 | Done
53 | S1ID2025060419WBF1-6 | SUM-AC-JTH-0549_SUM-AC-SAB-0473 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Swap Upgrade 2+0 | OUTBOUND DONE | 591KM | 350000266071 | Transportation service between Medan WH and Kota Sabang,Truck | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-11 | Done
54 | S1ID2025060419WBF1-8 | SUM-AC-LSK-0023_SUM-AC-LSK-0142 | North Sumatra | ADIONO | Nanggroe Aceh | New Link 2+0 | OUTBOUND DONE | 319KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-01-09 | Done
55 | S1ID2025060419WBF1-8 | SUM-AC-STR-0027_SUM-AC-STR-0206 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | New Link 2+0 | OUTBOUND DONE | 363KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-01-09 | Done
56 | S1ID2025060419WBF1-8 | SUM-AC-STR-0006_SUM-AC-TKN-0210 | North Sumatra | ADIONO | Nanggroe Aceh | New Link 2+0 | OUTBOUND DONE | 432KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-01-09 | Done
57 | S1ID2025060419WBF1-8 | SUM-AC-STR-0018_SUM-AC-STR-0206 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | OUTBOUND DONE | 433KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-01-09 | Done
58 | S1ID2025060419WBF1-8 | SUM-AC-STR-0022_SUM-AC-STR-0206 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | New Link 2+0 | OUTBOUND DONE | 345KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
59 | S1ID2025060419WBF1-7 | ZMDN_4664_NMDN_0058 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
60 | S1ID2025060419WBF1-7 | NMDN_0677_ZMDN_4036 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
61 | S1ID2025060419WBF1-8 | SUM-AC-STR-0005_SUM-AC-TKN-0210 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 517KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
62 | S1ID2025060419WBF1-8 | SUM-AC-LSK-0065_SUM-AC-LSK-0147 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 369KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-01-09 | Done
63 | S1ID2025060419WBF1-8 | SUM-AC-STR-0004_SUM-AC-STR-0215 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 427KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
64 | S1ID2025060419WBF1-8 | SUM-AC-SGI-0021_SUM-AC-SGI-0692 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | New Link 2+0 | Outbound Done | 517KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
65 | S1ID2025060419WBF1-7 | NMDN_0874_NMDN_0102 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
66 | S1ID2025060419WBF1-11 | SUM-AC-STR-0008_SUM-AC-STR-0382 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 440km | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
67 | S1ID2025060419WBF1-8 | SUM-AC-SGI-0005_SUM-AC-SGI-0429 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | New Link 2+0 | Outbound Done | 517KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
68 | S1ID2025060419WBF1-8 | SUM-AC-MRN-0005_SUM-AC-MRN-0522 | North Sumatra | ADIONO | Nanggroe Aceh | New Link 2+0 | Outbound Done | 474KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
69 | S1ID2025060419WBF1-7 | SUM-AC-KRB-2398_SUM-AC-KRB-0089 | North Sumatra | ADIONO | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 154KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
70 | S1ID2025060419WBF1-7 | SUM-AC-KRB-1312_SUM-AC-KRB-0085 | North Sumatra | ADIONO | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE | 157KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
71 | S1ID2025060419WBF1-8 | SUM-AC-STR-0025_SUM-AC-STR-0214 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 433KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
72 | S1ID2025060419WBF1-8 | SUM-AC-LSK-0039_SUM-AC-LSK-0567 | North Sumatra | ADIONO | Nanggroe Aceh | New Link 2+0 | Outbound Done | 322KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
73 |  | SUM-SU-AKK-2719_SUM-SU-AKK-1124 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 273 KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1 Trip | 1000000
74 | S1ID2025060419WBF1-7 | SUM-SU-KPI-2423_SUM-SU-KPI-1145 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2025-11-18 | Done
75 | S1ID2025060419WBF1-12 | SUM-SU-TJB-2211_SUM-SU-TJB-1412 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
76 | S1ID2025060419WBF1-12 | SUM-SU-TJB-0184_SUM-SU-TJB-1417 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
77 | S1ID2025060419WBF1-12 | SUM-SU-KIS-0136_SUM-SU-KIS-0157 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
78 | S1ID2025060419WBF1-12 | SUM-SU-AKK-1116_SUM-SU-KIS-0147 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
79 | S1ID2025060419WBF1-12 | SUM-SU-TJB-0186_SUM-SU-TJB-1415 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
80 | S1ID2025060419WBF1-12 | ZMDN_4595_ZMDN_5408 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 159 KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
81 | S1ID2025060419WBF1-12 | SUM-SU-KIS-2227_SUM-SU-KIS-0159 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
82 | S1ID2025060419WBF1-12 | SUM-SU-AKK-2251_SUM-SU-AKK-0003 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
83 | S1ID2025060419WBF1-12 | SUM-SU-AKK-2253_SUM-SU-AKK-0001 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 231 KM | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
84 | S1ID2025060419WBF1-8 | SUM-AC-JTH-0001_SUM-AC-JTH-0392 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 579 KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-01-09 | Done
85 | S1ID2025060419WBF1-8 | SUM-AC-LSK-0042_SUM-AC-LSK-0260 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | New Link 2+0 | Outbound Done | 324 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
86 | S1ID2025060419WBF1-8 | SUM-AC-LSK-0016_SUM-AC-LSK-0134 | North Sumatra | RICARDO SINAGA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 331 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
87 | S1ID2025060419WBF1-8 | SUM-AC-STR-0030_SUM-AC-STR-0208 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 440 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
88 | S1ID2025060419WBF1-8 | SUM-AC-STR-0010_SUM-AC-STR-0215 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 426 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
89 | S1ID2025060419WBF1-8 | SUM-AC-LSK-0041_SUM-AC-LSK-0132 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | New Link 2+0 | Outbound Done | 340 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
90 | S1ID2025060419WBF1-9 | SUM-AC-LSK-0058_SUM-AC-LSK-0139 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 316 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-03-02 | Done
91 | S1ID2025060419WBF1-10 | SUM-AC-LSK-0037_SUM-AC-LSM-0467 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 358 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-10 | Done
92 | S1ID2025060419WBF1-10 | SUM-AC-LSK-0021_SUM-AC-LGS-2326 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done | 315 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-10 | Done
93 | S1ID2025060419WBF1-11 | SUM-AC-KRB-0012_SUM-AC-KRB-1309 | North Sumatra | FERNANDO | Nanggroe Aceh | New Link 2+0 | Outbound Done | 161 KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
94 | S1ID2025060419WBF1-11 | SUM-AC-KRB-0027_SUM-AC-KRB-0085 | North Sumatra | FERNANDO | Nanggroe Aceh | New Link 2+0 | Outbound Done | 166 KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
95 | S1ID2025060419WBF1-8 | SUM-AC-JTH-0006_SUM-AC-JTH-0069 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | Reroute 2+0 | Outbound Done | 668 KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
96 | S1ID2025060419WBF1-8 | SUM-AC-JTH-0004_SUM-AC-JTH-0079 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | Reroute 2+0 | Outbound Done | 584 KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
97 | S1ID2025060419WBF1-10 | SUM-AC-LSK-0033_SUM-AC-LSK-0132 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Reroute 2+0 | Outbound Done | 341 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-10 | Done
98 | S1ID2025060419WBF1-8 | SUM-AC-LSM-0005_SUM-AC-LSK-0151 | North Sumatra | RUDI GUNAWAN | Nanggroe Aceh | Reroute 2+0 | Outbound Done | 351 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
99 | S1ID2025060419WBF1-8 | ZMDN_4840_SUM-SU-SRH-1289 | North Sumatra | ARIF MARPAUNG | North Sumatra | Reroute 2+0 | Outbound Done | 65 KM | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
100 | S1ID2025060419WBF1-8 | ZMDN_4618_SUM-SU-LMP-0479 | North Sumatra | ANGGA WIJAYA | North Sumatra | Reroute 2+0 | Outbound Done | 133 KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
101 | S1ID2025060419WBF1-8 | ZMDN_5322_SUM-SU-LMP-0469 | North Sumatra | RUDI GUNAWAN | North Sumatra | Reroute 2+0 | Outbound Done | 121 KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
102 | S1ID2025060419WBF1-12 | SUM-SU-PSP-2157_SUM-SU-PSP-1046 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 343 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
103 | S1ID2025060419WBF1-14 | SUM-SU-PYB-2166_SUM-SU-PYB-1762 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND IN PROSES | 493 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
104 | S1ID2025060419WBF1-14 | SUM-SU-PSP-1020_SUM-SU-PSP-1752 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND IN PROSES | 385 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
105 | S1ID2025060419WBF1-14 | SUM-SU-PSP-2159_SUM-SU-PSP-1036 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 363 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
106 | S1ID2025060419WBF1-14 | SUM-SU-PYB-1075_SUM-SU-PYB-1081 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE | 566 KM | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
107 | S1ID2025060419WBF1-12 | SUM-SU-KBJ-0121_SUM-SU-PMS-0898 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
108 | S1ID2025060419WBF1-12 | SUM-SU-PMS-0928_SUM-SU-PMS-0942 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
109 |  | SUM-SU-KIS-2229_SUM-SU-KIS-0156 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1 Trip | 1000000
110 | S1ID2025060419WBF1-12 | SUM-SU-AKK-2248_SUM-SU-AKK-0163 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
111 | S1ID2025060419WBF1-12 | SUM-SU-AKK-2255_SUM-SU-AKK-1117 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
112 | S1ID2025060419WBF1-12 | SUM-SU-KBJ-2234_SUM-SU-KBJ-0121 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
113 | S1ID2025060419WBF1-8 | SUM-AC-LSK-0031_SUM-AC-LSK-0561 | North Sumatra | RUDI GUNAWAN | Nanggroe Aceh | New Link 2+0 | Outbound Done | 367 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-01-09 | Done
114 | S1ID2025060419WBF1-8 | SUM-SU-PMS-0039_SUM-SU-PMS-0913 | North Sumatra | TEAM EXTERNAL | Nanggroe Aceh | New Link 2+0 | Outbound Done | 146 KM | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-01-09 | Done
115 | S1ID2025060419WBF1-8 | SUM-SU-DLS-0016_SUM-SU-TRT-1424 | North Sumatra | RICARDO SINAGA | North Sumatra | New Link 2+0 | Outbound Done |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-01-09 | Done
116 | S1ID2025060419WBF1-8 | SUM-AC-LSK-0017_SUM-AC-LSK-0145 | North Sumatra | ANGGA WIJAYA | North Sumatra | New Link 2+0 | Outbound Done | 452 KM | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-01-09 | Done
117 |  | SUM-SU-KBJ-0103_SUM-SU-KBJ-0096 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 1 Trip | 1000000
118 | S1ID2025060419WBF1-12 | SUM-SU-KBJ-2652_SUM-SU-KBJ-0103 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
119 | S1ID2025060419WBF1-14 | SUM-SU-AKK-1537_SUM-SU-AKK-1141 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km | 1 Trip | 1000000 | 1 Trip | 1000000 | Done | 1000000 | 2026-04-21 | Done
120 | S1ID2025060419WBF1-12 | SUM-SU-KBJ-0070_SUM-SU-KBJ-0072 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
121 | S1ID2025060419WBF1-12 | SUM-SU-KBJ-0072_SUM-SU-KBJ-0074 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
122 | S1ID2025060419WBF1-12 | SUM-SU-AKK-1678_SUM-SU-AKK-0008 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
123 | S1ID2025060419WBF1-14 | ZMDN_5322_SUM-SU-LMP-0469 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
124 |  | SUM-SU-KBJ-0091_SUM-SU-KBJ-0096 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 1 Trip | 1000000
125 |  | SUM-SU-PMS-2637_SUM-SU-PMS-0952 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1 Trip | 1000000
126 |  | ZMDN_4836_NMDN_0155 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1 Trip | 1000000
127 | S1ID2025060419WBF1-12 | SUM-SU-AKK-2444_SUM-SU-AKK-1119 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
128 |  | SUM-SU-AKK-2138_SUM-SU-AKK-1168 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1 Trip | 1000000
129 |  | SUM-SU-AKK-2208_SUM-SU-AKK-1157 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1 Trip | 1000000
130 | S1ID2025060419WBF1-14 | ZMDN_4618_SUM-SU-LMP-0479 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
131 |  | ZMDN_5346_NMDN_0103 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1 Trip | 1000000
132 |  | SUM-SU-TRT-2014_SUM-SU-TRT-1428 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1 Trip | 1000000
133 |  | SUM-SU-TRT-2016_SUM-SU-TRT-1432 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1 Trip | 1000000
134 | S1ID2025060419WBF1-14 | SUM-SU-TRT-1442_SUM-SU-TRT-1430 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND IN PROSES |  | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
135 |  | SUM-SU-PMS-0911_SUM-SU-PMS-0935 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1 Trip | 1000000
136 |  | SUM-SU-PMS-0918_SUM-SU-PMS-0962 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1 Trip | 1000000
137 | S1ID2025060419WBF1-14 | SUM-SU-SRH-1266_SUM-SU-PMS-0962 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
138 |  | SUM-SU-SRH-1273_SUM-SU-PMS-0962 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km<Distance≤100km) | 1 Trip | 1000000 | 1 Trip | 1000000
139 | S1ID2025060419WBF1-10 | SUM-AC-BIR-0030_SUM-AC-BIR-0374 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | New Link 2+0 | Outbound Done |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-10 | Done
140 | S1ID2025060419WBF1-10 | SUM-SU-PMS-0033_SUM-SU-PMS-0909 | North Sumatra | RICARDO SINAGA | North Sumatra | New Link 2+0 | Outbound Done |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-10 | Done
141 | S1ID2025060419WBF1-11 | SUM-SU-PMS-0031_SUM-SU-KIS-2129 | North Sumatra | RICARDO SINAGA | North Sumatra | New Link 2+0 | Outbound Done |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
142 | S1ID2025060419WBF1-15 | NMDN_0034_SUM-SU-LBP-0411 | North Sumatra | RICARDO SINAGA | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1.4 | 1000000
143 | S1ID2025060419WBF1-15 | NMDN_0739_SUM-SU-LBP-0227 | North Sumatra | RUDI GUNAWAN | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1.4 | 1000000
144 | S1ID2025060419WBF1-15 | NMDN_0707_SUM-SU-LBP-0308 | North Sumatra | RICARDO SINAGA | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1.4 | 1000000
145 | S1ID2025060419WBF1-13 | NMDN_0746_SUM-SU-LBP-0367 | North Sumatra | RICARDO SINAGA | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000 | Done | 1000000 | 2026-04-21 | Done
146 | S1ID2025060419WBF1-15 | NMDN_0402_SUM-SU-LBP-0505 | North Sumatra | RUDI GUNAWAN | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1.4 | 1000000
147 | S1ID2025060419WBF1-13 | ZMDN_4118_SUM-SU-LBP-0338 | North Sumatra | RICARDO SINAGA | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
148 | S1ID2025060419WBF1-14 | NMDN_0517_SUM-SU-PSP-1217 | North Sumatra | RUDI GUNAWAN | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
149 | S1ID2025060419WBF1-13 | ZMDN_4944_SUM-SU-MDN-0573 | North Sumatra | FERNANDO | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
150 | S1ID2025060419WBF1-13 | ZMDN_5327_SUM-SU-MDN-0299 | North Sumatra | RICARDO SINAGA | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.3 | 1000000 | Done | 1000000 | 2026-04-21 | Done
151 | S1ID2025060419WBF1-14 | SUM-SU-AKK-2719_SUM-SU-AKK-1120 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
152 | S1ID2025060419WBF1-12 | SUM-SU-PMS-2106_SUM-SU-PMS-0959 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-02-03 | Done
153 | S1ID2025060419WBF1-12 | SUM-SU-PMS-2335_SUM-SU-PMS-0920 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-02-03 | Done
154 | S1ID2025060419WBF1-14 | SUM-SU-GNT-0071_SUM-SU-SBH-1068 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
155 | S1ID2025060419WBF1-14 | ZMDN_4999_NMDN_0100 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
156 |  | ZMDN_4654_ZMDN_4876 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
157 |  | ZMDN_5414_NMDN_0985 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
158 |  | ZMDN_4697_ZMDN_4178 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
159 |  | NMDN_0402_NMDN_0275 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND IN PROSES |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
160 | S1ID2025060419WBF1-14 | ZMDN_5341_SUM-SU-PMS-0946 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND IN PROSES |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
161 |  | SUM-SU-LMP-0993_SUM-SU-LMP-0457 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1 Trip | 1000000
162 |  | SUM-AC-JTH-0623_SUM-AC-JTH-0606 | North Sumatra | ANGGA WIJAYA | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000
163 |  | NMDN_0102_NMDN_0828 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1 Trip | 1000000
164 |  | NMDN_0746_NMDN_0322 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
165 | S1ID2025060419WBF1-14 | ZMDN_4715_SUM-SU-LBP-0302 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
166 |  | ZMDN_5327_NMDN_0240 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
167 |  | ZMDN_4907_NMDN_0265 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
168 |  | NMDN_0156_ZMDN_4183 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND IN PROSES |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
169 |  | SUM-SU-SBH-0081_SUM-SU-SBH-1220 | North Sumatra | RUDI GUNAWAN | North Sumatra | Dismantle MW Keep | INBOUND IN PROSES |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1 Trip | 1000000
170 | S1ID2025060419WBF1-15 | NMDN_0097_SUM-SU-LBP-0337 | North Sumatra | RUDI GUNAWAN | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1.4 | 1000000
171 | S1ID2025060419WBF1-13 | ZMDN_4715_SUM-SU-LBP-0302 | North Sumatra | RUDI GUNAWAN | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1.4 | 1000000
172 | S1ID2025060419WBF1-14 | SUM-SU-SBG-1188_SUM-SU-SBG-1190 | North Sumatra | RICARDO SINAGA | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
173 | S1ID2025060419WBF1-15 | SUM-SU-PYB-1076_SUM-SU-PYB-1079 | North Sumatra | RUDI GUNAWAN | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000
174 | S1ID2025060419WBF1-15 | SUM-SU-PSP-1046_SUM-SU-PSP-1544 | North Sumatra | RUDI GUNAWAN | North Sumatra | Reroute 2+0 | Outbound Done |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000
175 | S1ID2025060419WBF1-13 | SUM-SU-SBG-2227_SUM-SU-SBG-1185 | North Sumatra | RICARDO SINAGA | North Sumatra | Swap Upgrade 2+0 | Outbound Done |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1 Trip | 1000000 | Done | 1000000 | 2026-04-21 | Done
176 | S1ID2025060419WBF1-15 | SUM-SU-SBH-0081_SUM-SU-SBH-1220 | North Sumatra | RICARDO SINAGA | North Sumatra | Swap Upgrade 2+0 | Outbound Done |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000
177 | S1ID2025060419WBF1-14 | SUM-SU-PRR-2221_SUM-SU-PRR-1002 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
178 |  | SUM-AC-BIR-0593_SUM-AC-BIR-0004 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | Dismantle MW Keep |  |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000
179 | S1ID2025060419WBF1-14 | SUM-AC-BIR-0011_SUM-AC-BIR-0352 | North Sumatra | ANGGA WIJAYA | Nanggroe Aceh | Dismantle MW Keep | INBOUND DONE |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
180 | S1ID2025060419WBF1-13 | NMDN_0517_SSBG0002 | North Sumatra | ANGGA WIJAYA | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
181 | S1ID2025060419WBF1-14 | SUM-SU-PYB-1076_SUM-SU-PYB-1079 | North Sumatra | ANGGA WIJAYA | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
182 | S1ID2025060419WBF1-14 | SUM-SU-KIS-2224_SUM-SU-KIS-0177 | North Sumatra | ANGGA WIJAYA | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
183 | S1ID2025060419WBF1-13 | SUM-SU-SBG-1188_SUM-SU-SBG-1187 | North Sumatra | RICARDO SINAGA | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1 Trip | 1000000 | Done | 1000000 | 2026-04-21 | Done
184 | S1ID2025060419WBF1-14 | SUM-SU-SBG-2227_SUM-SU-SBG-1185 | North Sumatra | RICARDO SINAGA | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
185 | S1ID2025060419WBF1-14 | NMDN_0097_NMDN_0238 | North Sumatra | VALDINO RAWUNG | North Sumatra | Dismantle MW Keep | INBOUND DONE |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
186 |  | SUM-AC-JTH-0602_SUM-AC-JTH-0392 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Dismantle MW Keep |  |  | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000
187 |  | SUM-AC-JTH-0080_SUM-AC-JTH-0077 | North Sumatra | VALDINO RAWUNG | Nanggroe Aceh | Dismantle MW Keep |  |  | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000
188 |  | SUM-SU-DLS-8021_SUM-SU-DLS-0062 | North Sumatra | RUDI GUNAWAN | North Sumatra | Dismantle MW Keep |  |  | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000
189 |  | SUM-SU-TRT-2015_SUM-SU-TRT-2008 | North Sumatra | RUDI GUNAWAN | North Sumatra | Dismantle MW Keep |  |  | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1 Trip | 1000000
190 |  | NMDN_0802_ZMDN_4200 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep |  |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
191 |  | NMDN_0034_ZMDN_5288 | North Sumatra | RICARDO SINAGA | North Sumatra | Dismantle MW Keep |  |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
192 |  | SUM-SU-PSP-1046_SUM-SU-PSP-1023 | North Sumatra | RUDI GUNAWAN | North Sumatra | Dismantle MW Keep |  |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1 Trip | 1000000
193 |  | ZMDN_4118_ZMDN_4168 | North Sumatra | WAHYU WIBISONO | North Sumatra | Dismantle MW Keep |  |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
194 |  | ZMDN_4085_NMDN_0133 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep |  |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
195 |  | ZMDN_4088_ZMDN_4112 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep |  |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
196 |  | SUM-SU-MDN-2635_SUM-SU-MDN-0697 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep |  |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1 Trip | 1000000
197 |  | NMDN_0703_NMDN_0225 | North Sumatra | TEAM EXTERNAL | North Sumatra | Dismantle MW Keep |  |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
198 |  | SUM-SU-PMS-1889_SUM-SU-PMS-0981 | North Sumatra | NOT YET SIGN TO TEAM | North Sumatra | Dismantle MW Keep |  |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000
199 |  | ZMDN_4045_ZMDN_5288 | North Sumatra | RICARDO SINAGA | North Sumatra | Dismantle MW Keep |  |  | 350000265952 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,Distance≤50km) | 1 Trip | 1000000 | 1 Trip | 1000000
200 |  | SUM-SU-AKK-0010_SUM-SU-AKK-1109 | North Sumatra | NOT YET SIGN TO TEAM | North Sumatra | New Link 2+0 |  |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000
201 |  | SUM-AC-KTN-0382_SUM-AC-KTN-0103 | North Sumatra | RUDI GUNAWAN | Nanggroe Aceh | Dismantle MW Keep |  |  | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km<Distance≤300km) | 1 Trip | 1000000 | 1.4 | 1000000
202 |  | SUM-AC-JTH-0623_SUM-AC-JTH-0606 | North Sumatra |  | Nanggroe Aceh | Swap Upgrade 2+0 SD |  |  | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000
203 | S1ID2025060419WBF1-13 | SUM-AC-JTH-0080_SUM-AC-JTH-0553 | North Sumatra |  | Nanggroe Aceh | Reroute 2+0 | Outbound Done |  | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000 | Done | 1000000 | 2026-04-21 | Done
204 | S1ID2025060419WBF1-13 | SUM-AC-SAB-0455_SUM-AC-SAB-0172 | North Sumatra | FERNANDO | Nanggroe Aceh | Swap Upgrade 2+0 | Outbound Done |  | 350000266071 | Transportation service between Medan WH and Kota Sabang,Truck | 1 Trip | 1000000 | 2 | 1000000 | Done | 1000000 | 2026-04-21 | Done
205 | S1ID2025060419WBF1-16 | SUM-AC-JTH-0602_SUM-AC-JTH-0080 | North Sumatra |  | Nanggroe Aceh | Reroute 2+0 |  |  | 350000265962 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,500km<Distance≤800km) | 1 Trip | 1000000 | 1.4 | 1000000
206 |  | SUM-AC-SAB-0172_SUM-AC-SAB-0473 | North Sumatra | FERNANDO | Nanggroe Aceh | New Link 2+0 |  |  | 350000266071 | Transportation service between Medan WH and Kota Sabang,Truck | 1 Trip | 1000000 | 2 | 1000000
207 | S1ID2025060419WBF1-15 | SUM-SU-AKK-0016_SUM-SU-AKK-1152 | North Sumatra | ANGGA WIJAYA | North Sumatra | New Link 2+0 |  |  | 350000265960 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,300km<Distance≤500km) | 1 Trip | 1000000 | 1.4 | 1000000
208 |  | SUM-SU-AKK-0016 | North Sumatra | FERNANDO | North Sumatra | NEW SITE |  |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000
209 |  | SUM-SU-AKK-0058 | North Sumatra | NOT YET SIGN TO TEAM | North Sumatra | NEW SITE |  |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000
210 |  | SUM-SU-AKK-0058_SUM-SU-AKK-1681 | North Sumatra | NOT YET SIGN TO TEAM | North Sumatra | New Link 2+0 |  |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000
211 |  | SUM-SU-TJB-0001 | North Sumatra | RINALDI | North Sumatra | NEW SITE |  |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000
212 |  | SUM-SU-AKK-0010 | North Sumatra | NOT YET SIGN TO TEAM | North Sumatra | NEW SITE |  |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000
213 | S1ID2025060419WBF1-15 | ENT-SU-AKK-0006_SUM-SU-AKK-2001 | North Sumatra | ANGGA WIJAYA | North Sumatra | Reroute 2+0 |  |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 1.4 | 1000000
214 | S1ID2025060419WBF1-15 | SUM-SU-PMS-0906_SUM-SU-PMS-0912 | North Sumatra | RICARDO SINAGA | North Sumatra | Reroute 2+0 |  |  | 350000265956 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,100km<Distance≤200km) | 1 Trip | 1000000 | 2 | 1000000
215 | S1ID2025060419WBF1-15 | SUM-SU-AKK-0061_SUM-SU-AKK-0042 | North Sumatra |  | North Sumatra | New Link 2+0 |  |  | 350000265958 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,200km | 1 Trip | 1000000 | 1.4 | 1000000
216 | S1ID2025060419WBF1-15 | SUM-SU-STB-2203_SUM-SU-STB-1389 | North Sumatra |  | North Sumatra |  |  |  | 350000265954 | Transportation service between ZTE Warehouse and exact site location in Sumatra inland areas(Pickup,50km | 1 Trip | 1000000 | 2 | 1000000