## Assignment
Catatan bebas | NO | Assigment Date | PO NUMBER | DUID | DU NAME | Plan Start | Target Days | Actual Finish Work | LONG AGING | Delay Reason | REMARK PROGRESS | PIC TEAM | SOW GROUP | DETAIL SOW | SUB REGION | REGION | ITEM PO | PO DESCRIPTION | AMOUNT | NEW SITE - RAN - DETAIL AMOUNT | STATUS PROGRESS ON SITE | STATUS MATERIAL | DOC. SUBMISSION | SITE ON-AIR | TERM 40% | DATE | ATP | TERM 50% | DATE2 | PAC | TERM 10% | DATE3 | WCC | TERM 100% | DATE4 | FULL PAYMENT Termin | FULL AMPUNT 100% | FULL PAYMENT2 ALL | OUTSTANDING PO | REMARKS | STO Remarks | Nilai di PO | Column1 | X | DUID BASE ON PO | CURRENT STATUS | Daily Progress | PIC Incharge | REMARK | ZTE TARGET | REMARK WCC
| 1 | 2025-07-21 | S1ID2025042515WBF1-1 | NACH_0010_SUM-AC-BNA-0228 | Lamteh-KMulia SHUB(G) | 2025-07-28 | 2 Days | 2025-08-01 | 5 Days | Waiting Kunci MS>>MS still PM |  | ADIONO | Dismantle MW Keep | Dismantle MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-09-15 | Done | 500000 | 2025-10-08 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-BNA-2380_SUM-AC-BNA-0228 | Closed_TERM 3 |  |  | WCC_DOC NOT YET CLOSED |  | Need Open Task PAC, Submit DR Upload
| 2 | 2025-07-21 | S1ID2025042515WBF1-1 | NACH_0034_SUM-AC-BNA-0230 | Dayah RM_Ajuen-KMulia SHUB(G) | 2025-07-27 | 2 Days | 2025-07-28 | 2 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2025-09-15 | Done | 500000 | 2025-10-08 | Done | 100000 | 2026-01-26 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | NACH_0034_SUM-AC-BNA-0230 | L1 Approved
| 3 | 2025-07-30 | S1ID2025042515WBF1-1 | NACH_0044_SUM-AC-LSM-0158 | Mon Geudong-Kenari Lhokseumawe | 2025-07-26 | 2 Days | 2025-07-26 | 1 Days |  |  | VALDINO RAWUNG | Dismantle MW Keep | Dismantle MW 0.3 | Nanggroe Aceh | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-09-15 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-LSM-2403_SUM-AC-LSM-0158 | Closed_TERM 2-3 |  |  |  |  | Need Open Task PAC, Submit DR Upload
| 4 | 2025-07-30 | S1ID2025042515WBF1-1 | NACH_0053_SUM-AC-JTH-0082 | Saree HUB-Cinta Alam Lamtamot | 2025-07-31 | 2 Days | 2025-07-31 | 1 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 0.9 | Nanggroe Aceh | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-09-15 | Done | 500000 | 2025-10-08 | Done | 100000 | 2026-01-26 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | SUM-AC-JTH-2424_SUM-AC-JTH-0082 | Closed
| 5 | 2025-07-21 | S1ID2025042515WBF1-1 | NACH_0059_SUM-AC-BNA-0232 | Jalan Sawah-Dayah RM_Ajuen | 2025-07-25 | 2 Days | 2025-07-26 | 2 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-09-15 | Done | 500000 | 2025-10-08 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-BNA-2382_SUM-AC-BNA-0232 | Closed_TERM 3 |  |  | WCC_DOC NOT YET CLOSED |  | Need Open Task PAC, Submit DR Upload
| 6 | 2025-07-30 | S1ID2025042515WBF1-1 | NACH_0071_SUM-AC-LSK-0146 | B2S Madat-Lhoksukun 2 | 2025-07-24 | 2 Days | 2025-07-25 | 2 Days |  |  | VALDINO RAWUNG | Dismantle MW Keep | Dismantle MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-09-15 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-LSK-2433_SUM-AC-LSK-0146 | Closed_TERM 3 |  |  | WCC_DOC NOT YET CLOSED |  | Need Open Task PAC, Submit DR Upload
| 7 | 2025-07-21 | S1ID2025042515WBF1-1 | NACH_0124_SUM-AC-BNA-0032 | Batoh 2-Ateuk Jawo(G) | 2025-07-29 | 2 Days | 2025-07-29 | 1 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 0.3 | Nanggroe Aceh | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2025-09-15 | Done | 500000 | 2025-10-08 | Done | 100000 | 2026-01-26 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | NACH_0124_SUM-AC-BNA-0032 | L1 Approved
| 8 | 2025-07-21 | S1ID2025042515WBF1-6 | NACH_0022_SUM-AC-JTH-0287 | MUERAXA-WGW Smartfren_SPRHUB-IPBB | 2025-09-20 | 2 Days | 2025-09-20 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | Nanggroe Aceh | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2025-10-16 | Done | 500000 | 2025-10-27 | Done | 100000 | 2026-02-10 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done | Approver reject L2, Site Id berbeda |  |  |  | NACH_0022_SUM-AC-JTH-0287 | L1 Approved |  |  | 0605 Approver reject L2, Site Id berbeda 0705 Doc Submit | Dismantle
| 9 | 2025-08-04 | S1ID2025042515WBF1-7 | NMDN_0874_SUM-SU-LMP-0462 | Dusun Seroja-Indrapura | 2025-08-10 | 1 Days | 2025-08-13 | 4 Days | Waiting Kunci MS>>MS still Troubleshoot Outer city |  | ADIONO | Survey | MW LOS survey | North Sumatra | North Sumatra | 350000190099 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Closed | [9 empty] | Done | 1000000 | 2025-09-26 | 0 | 1000000 | 1000000 | 0 | Done |  |  |  |  | NMDN_0874_SUM-SU-LMP-0462 | Closed
| 10 | 2025-08-04 | S1ID2025042515WBF1-3 | ZMDN_5322_SUM-SU-LMP-0469 | LIMAPULUH-Lima Puluh | 2025-08-08 | 1 Days | 2025-08-08 | 1 Days |  |  | VALDINO RAWUNG | Survey | MW LOS survey | North Sumatra | North Sumatra | 350000198247 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Closed | [9 empty] | Done | 1000000 | 2025-08-29 | 0 | 1000000 | 1000000 | 0 | Done |  |  |  |  | ZMDN_5322_SUM-SU-LMP-0469 | Closed
| 11 | 2025-08-04 | S1ID2025042515WBF1-2 | SUM-SU-LMP-1657_SUM-SU-LMP-0475 | Perk Tanah Itam Ulu Batu Bara-Simpang Dolok | 2025-08-09 | 1 Days | 2025-08-09 | 1 Days |  |  | VALDINO RAWUNG | Survey | MW LOS survey | North Sumatra | North Sumatra | 350000198247 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Closed | [9 empty] | Done | 1000000 | 2025-08-29 | 0 | 1000000 | 1000000 | 0 | Done |  |  |  |  | SUM-SU-LMP-1657_SUM-SU-LMP-0475 | Closed
| 12 | 2025-08-04 | S1ID2025042515WBF1-2 | SUM-SU-LMP-0993_SUM-SU-LMP-0457 | Bandar Tinggi-LAUT TADOR NOM | 2025-08-07 | 1 Days | 2025-08-08 | 2 Days | 1/2 HOP |  | TEAM EXTERNAL | Survey | MW LOS survey | North Sumatra | North Sumatra | 350000190098 | MW Technical site survey&Design | 1000000 |  | Done | N/A | Closed | [9 empty] | Done | 1000000 | 2025-08-29 | 0 | 1000000 | 1000000 | 0 | Done |  |  |  |  | SUM-SU-LMP-0993_SUM-SU-LMP-0457 | Closed
| 13 | 2025-07-21 | S1ID2025042515WBF1-7 | SUM-AC-BIR-0593_SUM-AC-BIR-0271 | Peusangan BIREUEN Bawah-KUALA CEURAPE BIREUEN | 2025-07-30 | 1 Days | 2025-07-30 | 1 Days |  |  | VALDINO RAWUNG | Survey | MW LOS survey | Nanggroe Aceh | North Sumatra | 350000198247 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Closed | [9 empty] | Done | 1000000 | 2025-09-26 | 0 | 1000000 | 1000000 | 0 | Done |  |  |  |  | SUM-AC-BIR-0593_SUM-AC-BIR-0271 | Closed
| 14 | 2025-07-21 | S1ID2025042515WBF1-4 | SUM-AC-BIR-0593_SUM-AC-BIR-0271 | Peusangan BIREUEN Bawah-KUALA CEURAPE BIREUEN | 2025-09-19 | 4 Days | Done |  | OBU Faulty, Need change OBU |  | VALDINO RAWUNG | Reroute | Reroute 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2025-10-09 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-BIR-0593_SUM-AC-BIR-0271 | Closed_TERM 2-3
| 15 | 2025-07-21 | S1ID2025042515WBF1-4 | SUM-AC-BIR-0593_SUM-AC-BIR-0271 | Peusangan BIREUEN Bawah-KUALA CEURAPE BIREUEN | 2025-09-19 | 4 Days |  |  | OBU Faulty, Need change OBU |  | VALDINO RAWUNG | Reroute | Reroute 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2025-10-09 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-BIR-0593_SUM-AC-BIR-0271 | N/A
| 16 | 2025-07-21 | S1ID2025042515WBF1-2 | SUM-AC-BIR-0011_SUM-AC-BIR-0352 | JULI-PAYO ABO BIREUEN-PAYO ABO BIREUEN | 2025-07-31 | 1 Days | 2025-07-31 | 1 Days |  |  | VALDINO RAWUNG | Survey | MW LOS survey | Nanggroe Aceh | North Sumatra | 350000198247 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Closed | [9 empty] | Done | 1000000 | 2025-08-29 | 0 | 1000000 | 1000000 | 0 | Done |  |  |  |  | SUM-AC-BIR-0011_SUM-AC-BIR-0352 | Closed
| 17 | 2025-07-21 | S1ID2025042515WBF1-4 | SUM-AC-BIR-0011_SUM-AC-BIR-0352 | JULI-PAYO ABO BIREUEN | 2025-09-19 | 4 Days | 2025-09-26 | 7 Days |  |  | VALDINO RAWUNG | Reroute | Reroute 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2025-09-29 | Done | 500000 | 2025-12-22 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-BIR-0011_SUM-AC-BIR-0352 | Closed_TERM 3 |  |  | PL Picture 2.1.2.1 - Power Cable Connection need cek Picture 2.1.7.4 - TX Lev < Link Budget LB-22 On review site Down impact disaster Area aceh Picture 2.1.2.18 - Excess Optic Cable need Tis Plat |  | Need Open Task PAC_Need Cek CPL
| 18 | 2025-07-21 | S1ID2025042515WBF1-4 | SUM-AC-BIR-0011_SUM-AC-BIR-0352 | JULI-PAYO ABO BIREUEN | 2025-09-19 | 4 Days | 2025-09-26 | 7 Days |  |  | VALDINO RAWUNG | Reroute | Reroute 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2025-09-29 | Done | 500000 | 2025-12-22 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-BIR-0011_SUM-AC-BIR-0352 | N/A |  |  | WCC_NEED OPEN TASK PAC
| 19 | 2025-07-21 | S1ID2025042515WBF1-7 | SUM-AC-LSK-0105_SUM-AC-LSK-0146 | LANGKAHAN-PANTON LABU-PANTON LABU | 2025-07-26 | 1 Days | 2025-07-27 | 2 Days |  |  | VALDINO RAWUNG | Survey | MW LOS survey | Nanggroe Aceh | North Sumatra | 350000190098 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Closed | [9 empty] | Done | 1000000 | 2025-09-26 | 0 | 1000000 | 1000000 | 0 | Done |  |  |  |  | SUM-AC-LSK-0105_SUM-AC-LSK-0146 | Closed
| 20 | 2025-08-07 | Waiting Release | ZMDN_4656_ZMDN_4015 | PERTIGAAN RING ROAD-PERDAMAIAN | 2025-08-09 | 2 Days | 2025-08-09 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4656_ZMDN_4015 | Closed_Need PO
| 21 | 2025-08-07 | Waiting Release | ZMDN_4838_ZMDN_4015 | UJUNG BANDAR-PERDAMAIAN | 2025-08-10 | 2 Days | 2025-08-10 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4838_ZMDN_4015 | Closed_Need PO
| 22 | 2025-08-06 | S1ID2025042515WBF1-7 | NACH_0026_SUM-AC-LSM-0131 | Jalan SMKN 5-Poltek Lhokseumawe | 2025-08-09 | 1 Days | 2025-08-10 | 2 Days |  |  | ADIONO | Survey | MW LOS survey | Nanggroe Aceh | North Sumatra | 350000198247 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Closed | [9 empty] | Done | 1000000 | 2025-09-26 | 0 | 1000000 | 1000000 | 0 | Done |  |  |  |  | NACH_0026_SUM-AC-LSM-0131 | Closed
| 23 | 2025-08-12 | Waiting Release | NMDN_0021_ZMDN_4024 | Shamo Motor Kuala Bingai-Sekata | 2025-08-16 | 2 Days | 2025-08-17 | 2 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0021_ZMDN_4024 | Closed_Need PO
| 24 | 2025-08-14 | Waiting Release | NMDN_0073_NMDN_0195 | Bakaran Batu-Padang matingi | 2025-08-18 | 2 Days | 2025-08-18 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0073_NMDN_0195 | Closed_Need PO
| 25 | 2025-08-09 | S1ID2025042515WBF1-9 | SUM-AC-LSK-0105_SUM-AC-LSK-0146 | LANGKAHAN-PANTON LABU | 2025-08-14 | 4 Days | 2025-08-17 | 4 Days |  |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade 2+0_11G_SRU2_2+0 XPIC_0.9_0.9 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed with PL | Done | 400000 | 2025-09-09 | Done | 500000 | 2025-09-29 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-LSK-0105_SUM-AC-LSK-0146 | Plan On Site |  |  | LSK-0146 Permit Release Picture 2.1.7.13 - Grounding to Neutral Voltage Rect SUM-AC-LSK-0105 Eaton Picture 2.1.2.18 - Excess Optic Cable Need used Tis Plat Picture 2.1.3.2 – IDU Body & Port Picture 2.1.3.3 IDU Installation Picture 2.1.4.2 - ODU Body & Port Picture 2.1.4.3 - ODU Installation Picture 2.1.5.8 Antenna Fix Strut Rawan lepas | CPL | Need Open Task PAC_Need Cek CPL
| 26 | 2025-08-09 | S1ID2025042515WBF1-9 | SUM-AC-LSK-0105_SUM-AC-LSK-0146 | LANGKAHAN-PANTON LABU | 2025-08-14 | 4 Days | 2025-08-17 | 4 Days |  |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade 2+0_11G_SRU2_2+0 XPIC_0.9_0.9 | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2025-09-09 | Done | 500000 | 2025-09-29 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-LSK-0105_SUM-AC-LSK-0146 | N/A
| 27 | 2025-07-28 | S1ID2025042515WBF1-4 | SUM-AC-MRN-0527_SUM-AC-BIR-0002 | Lhok_pusong-samalaga | 2025-08-19 | 4 Days | 2025-08-24 | 6 Days |  |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2025-08-30 | Done | 500000 | 2025-10-09 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-MRN-0527_SUM-AC-BIR-0002 | Closed_TERM 3 |  |  | Picture 2.1.2.15 - IDU Grounding dari atas sampai bawah ? |  | Need Open Task PAC_Need Cek CPL
| 28 | 2025-07-28 | S1ID2025042515WBF1-4 | SUM-AC-MRN-0527_SUM-AC-BIR-0002 | Lhok_pusong-samalaga | 2025-08-19 | 4 Days | 2025-08-24 | 6 Days |  |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2025-08-30 | Done | 500000 | 2025-10-09 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-MRN-0527_SUM-AC-BIR-0002 | N/A
| 29 | 2025-08-28 | S1ID2025042515WBF1-5 | SUM-SU-AKK-1510_SUM-SU-AKK-1130 | PERS BINA RAGA LABUHAN BATU-Cendana Rntau Prapat | 2025-09-11 | 2 Days | 2025-09-11 | 1 Days |  |  | VALDINO RAWUNG | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-09-25 | Done | 500000 | 2025-10-16 | Done | 100000 | 2025-12-16 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | SUM-SU-AKK-1510_SUM-SU-AKK-1130 | Closed
| 30 | 2025-08-01 | S1ID2025042515WBF1-5 | SUM-SU-AKK-1517_SUM-SU-AKK-1129 | SIRANDURUNG (SIRONDANG) LABUHAN BATU-Rantau Parapat Infil | 2025-11-26 | 2 Days | 2025-11-27 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-16 | Done | 500000 | 2025-12-22 | Done | 100000 | 2026-04-13 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | SUM-SU-AKK-1517_SUM-SU-AKK-1129 | Closed
| 31 | 2025-08-25 | S1ID2025042515WBF1-6 | SUM-SU-AKK-2719_SUM-SU-AKK-1120 | AFDELING_II_RANTAUPRAPAT-Mpls - Rantau Prapat |  | 2 Days | Done |  |  |  | VALDINO RAWUNG | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-27 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-AKK-2719_SUM-SU-AKK-1120 | Reject_Term 10% Submit |  |  |  |  | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092
| 32 | 2025-08-28 | S1ID2025042515WBF1-5 | SUM-SU-KPI-2543_SUM-SU-KPI-1170 | ASAM JAWA TORGAMBA-Asam Jawa | 2025-11-27 | 2 Days | 2025-11-27 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle Ant 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-16 | Done | 500000 | 2025-12-22 | Done | 100000 | 2026-02-10 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | SUM-SU-KPI-2543_SUM-SU-KPI-1170 | Closed
| 33 | 2025-08-28 | S1ID2025042515WBF1-5 | SUM-SU-PSP-1020_SUM-SU-PSP-1752 | Simarpinggan-Rep LOSUNG BATU | Week 3 Januari 2026 | 2 Days | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep | DSM Ant 0.9 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-22 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-PSP-1020_SUM-SU-PSP-1752 | Closed_TERM 3 |  |  |  |  | Need Submit DR Upload & PAC
Perlu revisi PO | 34 | 2025-08-28 | S1ID2025042515WBF1-5 (need Revisi) | SUM-SU-PSP-2157_SUM-SU-PSP-1046 | PARAN DOLOK MARDOMU-Arse | 2026-01-15 | 2 Days | 2026-02-03 | 20 Days | Blocking Access | NE need extend permit, FE Done | TEAM EXTERNAL | Dismantle MW Keep | DSM Ant 1.8 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2025-12-22 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Po no 23, nillai di sheet rekap Po lebih kecil daripada di assigment | 1000000 | 0 |  | SUM-SU-PSP-2157_SUM-SU-PSP-1046 | L1 Approved | [5 empty] | S1ID2025042515WBF1-5 (need Revisi)
| 35 | 2025-08-28 | S1ID2025042515WBF1-5 | SUM-SU-PSP-2159_SUM-SU-PSP-1036 | ANGKOLA TIMUR HURABA- | 2026-01-14 | 2 Days | 2026-01-25 | 12 Days | Blocking Access | NE done, FE wating revisi permit | TEAM EXTERNAL | Dismantle MW Keep | DSM Ant 1.8(2)><Ant 1.2(2) | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-22 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-PSP-2159_SUM-SU-PSP-1036 | Reject_Term 10% Submit |  |  |  |  | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092
| 36 | 2025-08-23 | S1ID2025042515WBF1-9 | ZMDN_4740_SUM-SU-SDK-1235 | IBSNS_Add_006-1235_BATANG_BERUH | 2025-08-24 | 4 Days | 2025-08-30 | 7 Days | Perdana(Pilot) |  | ADIONO | Reroute | Reroute 2+0_23G_SRU2_2+0 XPIC_0.3_0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2025-09-09 | Done | 500000 | 2025-09-29 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-SDK-2793_SUM-SU-SDK-1235 | Closed_TERM 3 |  |  |  |  | Need Open Task PAC
| 37 | 2025-08-19 | Waiting Release | ZMDN_5415_ZMDN_4017 | Desa Namu Terasi Psr 5-Kotalimbaru Protelindo | 2025-08-21 | 2 Days | 2025-08-22 | 2 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_5415_ZMDN_4017 | Closed_Need PO
| 38 | 2025-08-29 | S1ID2025042515WBF1-8 | NMDN_0847_SUM-SU-KIS-0142 | Perkebunan Bandar Selamat_Bandar Pulau(Shub)(K) | 2025-08-26 | 2 Days | 2025-08-27 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-09-25 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-KIS-8210_SUM-SU-KIS-0142 | Closed_TERM 3 |  |  |  |  | Need Submit DR Upload & PAC
| 39 | 2025-08-29 | Waiting Release | ZMDN_4624_ZMDN_5379 | Pekan Bilah_NR_NEGRI LAMA | 2025-09-02 | 2 Days | 2025-09-02 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4624_ZMDN_5379 | Closed_Need PO
| 40 | 2025-08-09 | S1ID2025042515WBF1-9 | ZMDN_4740_SUM-SU-SDK-1235 | LANGKAHAN-PANTON LABU | 2025-08-24 | 4 Days | 2025-08-30 | 7 Days | Perdana(Pilot) |  | ADIONO | Reroute | Reroute 2+0_11G_SRU2_2+0 XPIC_0.9_0.9 | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2025-09-09 | Done | 500000 | 2025-09-29 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | ZMDN_4740_SUM-SU-SDK-1235 | N/A
| 41 | 2025-08-22 | S1ID2025042515WBF1-15 | ZMDN_5339_SUM-SU-DLS-0060 | Purba Manalu_SIMANGARONSANG | 2025-09-03 | 2 Days | 2025-09-03 | 1 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 1.2 dan 0.9 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-11-11 | Done | 500000 | 2025-11-18 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-DLS-8126_SUM-SU-DLS-0060 | Reject_Term 10% Submit |  |  |  |  | Reject_Term 10% Submit
| 42 | 2025-08-22 | S1ID2025042515WBF1-15 | ZMDN_5372_SUM-SU-BLG-0018 | BALIGE 2_BALIGE - TBG | 2025-09-01 | 2 Days | 2025-09-02 | 2 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-11-11 | Done | 500000 | 2025-11-18 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-BLG-2812_SUM-SU-BLG-0018 | Closed_TERM 3 |  |  |  |  | Need Open Task PAC, Submit DR Upload
| 43 | 2025-09-01 | S1ID2025042515WBF1-10 | SUM-AC-SGI-0177_SUM-AC-SGI-0182 | GarotP_Beureunen | 2025-09-13 | 4 Days | Done |  | NY take data QSCK |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-SGI-0177_SUM-AC-SGI-0182 | Closed_TERM 2 |  |  |  |  | Need Submit TERM2 ATP Approved(Auto)
| 44 | 2025-09-01 | S1ID2025042515WBF1-10 | SUM-AC-SGI-0177_SUM-AC-SGI-0182 | GarotP_Beureunen | 2025-09-13 | 4 Days |  |  | NY take data QSCK |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-SGI-0177_SUM-AC-SGI-0182 | N/A
| 45 | 2025-09-01 | S1ID2025042515WBF1-11 | SUM-AC-SGI-0273_SUM-AC-SGI-0181 | GEUNTENG TIMUR PIDIE_Sigli | 2025-09-05 | 4 Days | Done |  | NY take data QSCK |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade 2+0, Ant MW 0.9 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2025-10-16 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-SGI-0273_SUM-AC-SGI-0181 | Closed_Cek TERM 2
| 46 | 2025-09-01 | S1ID2025042515WBF1-11 | SUM-AC-SGI-0273_SUM-AC-SGI-0181 | GEUNTENG TIMUR PIDIE_Sigli | 2025-09-05 | 4 Days |  |  | NY take data QSCK |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade 2+0, Ant MW 0.9 | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2025-10-16 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-SGI-0273_SUM-AC-SGI-0181 | N/A
| 47 | 2025-09-01 | S1ID2025042515WBF1-11 | SUM-AC-SGI-0274_SUM-AC-SGI-0181 | GEUNTENG BARAT PIDIE_Sigli | 2025-09-06 | 4 Days | Done |  | Interference, ODU faulty, need change ODU |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2025-10-16 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-SGI-0274_SUM-AC-SGI-0181 | Closed_Cek TERM 2
| 48 | 2025-09-01 | S1ID2025042515WBF1-11 | SUM-AC-SGI-0274_SUM-AC-SGI-0181 | GEUNTENG BARAT PIDIE_Sigli | 2025-09-06 | 4 Days |  |  | Interference, ODU faulty, need change ODU |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2025-10-16 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-SGI-0274_SUM-AC-SGI-0181 | N/A
| 49 | 2025-08-28 | S1ID2025042515WBF1-15 | SUM-SU-AKK-2441_SUM-SU-AKK-1149 | LABUHANBATU UTARA MARBAU_Pangkatan | 2025-09-15 | 2 Days | 2025-09-16 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.8 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-11-11 | Done | 500000 | 2025-11-18 | Done | 100000 | 2025-12-16 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | SUM-SU-AKK-2441_SUM-SU-AKK-1149 | Closed
| 50 | 2025-08-28 | Waiting Release | SUM-SU-PYB-2166_SUM-SU-PYB-1762 | HUTA PUNGKUT JULU_MUARA PUNGKUT MANDAILING NATAL | Week 2 October 25 | 2 Days | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep | DSM Ant 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-PYB-2166_SUM-SU-PYB-1762 | Closed_Need PO
| 51 | 2025-08-28 | Waiting Release | SUM-SU-PYB-1075_SUM-SU-PYB-1081 | Batahan_Sinunukan | 2026-01-31 | 2 Days | 2026-02-01 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | DSM Ant 1.8 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-PYB-1075_SUM-SU-PYB-1081 | Closed_Need PO
| 52 | 2025-09-03 | S1ID2025042515WBF1-16 | ZMDN_5382_SUM-SU-SDK-1242 | Dolok Tolong_Dusun Damai | 2025-09-05 | 2 Days | 2025-09-06 | 2 Days |  |  | ADIONO | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-16 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-SDK-2799_SUM-SU-SDK-1242 | Reject_Term 10% Submit |  |  |  |  | Reject_Term 10% Submit
| 53 | 2025-09-07 | S1ID2025042515WBF1-15 | SUM-SU-AKK-1527_SUM-SU-AKK-1606 | PERS_CENDANA_LABUHAN_BATU | 2025-09-09 | 2 Days | 2025-09-09 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-11-11 | Done | 500000 | 2025-11-18 | Done | 100000 | 2025-12-16 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | SUM-SU-AKK-1527_SUM-SU-AKK-1606 | Closed
| 54 | 2025-09-07 | S1ID2025042515WBF1-15 | SUM-SU-AKK-2412_SUM-SU-AKK-1143 | BILAH BARAT_LABUHAN_BATU | 2025-09-09 | 2 Days | 2025-09-09 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-11-11 | Done | 500000 | 2025-11-18 | Done | 100000 | 2025-12-16 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | SUM-SU-AKK-2412_SUM-SU-AKK-1143 | Closed
| 55 | 2025-09-07 | S1ID2025042515WBF1-15 | SUM-SU-KIS-1802_SUM-SU-KIS-0139 | SITUNJAK ASAHAN_Pulau Rakyat Pekan | 2025-09-12 | 2 Days | 2025-09-12 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-11-11 | Done | 500000 | 2025-11-18 | Done | 100000 | 2025-12-16 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | SUM-SU-KIS-1802_SUM-SU-KIS-0139 | Closed
| 56 | 2025-09-07 | Waiting Release | NMDN_0075_NMDN_0167 | IBS_SMG-Aek Kanopan_Aek Loba Pekan | 2025-09-08 | 2 Days | 2025-09-08 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0075_NMDN_0167 | Closed_Need PO
| 57 | 2025-09-15 | Waiting Release | ZMDN_5404_ZMDN_5405 | SORPADA/Padang_Sidempuan2 | 2025-09-17 | 2 Days | 2025-09-17 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_5404_ZMDN_5405 | Closed_Need PO
| 58 | 2025-09-07 | S1ID2025042515WBF1-15 | ZMDN_4720_SUM-SU-KIS-0142 | AEK KUASAN/Aek Loba Pekan Kanopan | 2025-09-10 | 2 Days | 2025-09-10 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-11-11 | Done | 500000 | 2025-11-18 | Done | 100000 | 2026-02-10 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | ZMDN_4720_SUM-SU-KIS-0142 | Closed
| 59 | 2025-09-12 | S1ID2025042515WBF1-15 | SUM-SU-KPI-2426_SUM-SU-KPI-1646 | Sukadame Labuhanbatu Selatan_Perk Sei Rumbia | 2025-09-15 | 2 Days | 2025-09-15 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-11-11 | Done | 500000 | 2025-11-25 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-KPI-2426_SUM-SU-KPI-1646 | Closed_TERM 3 |  |  |  |  | Need Submit DR Upload & PAC
| 60 | 2025-09-18 | S1ID2025042515WBF1-57 | NACH_0093_SUM-AC-BNA-0043 | SF KUTA ALAM LUENG_MGW SMARTFREN | 2025-09-22 | 2 Days | 2025-09-27 | 6 Days | Team available onsite on 27 sept 25 |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.9 | Nanggroe Aceh | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NACH_0093_SUM-AC-BNA-0043 | Closed_Cek TERM 1
| 61 | 2025-09-23 | S1ID2025042515WBF1-16 | NMDN_0809_SUM-SU-BLG-0018 | COW SARIBURAJA_Balige | 2025-10-02 | 2 Days | 2025-10-02 | 1 Days | 1/2 HOP |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 1/2 Hop | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-16 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | NMDN_0809_SUM-SU-BLG-0018 | L1 Approved
| 62 | 2025-09-23 | S1ID2025042515WBF1-16 | NMDN_0854_SUM-SU-DLS-0062 | Desa Siponjot_Harian_2(HUB8)(I) | 2025-10-03 | 2 Days | 2025-10-03 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.3 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-16 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | NMDN_0854_SUM-SU-DLS-0062 | L1 Approved |  |  | 0605 Approver reject L2, Site Id berbeda 0705 Doc Submit | Dismantle
| 63 | 2025-09-23 | Waiting Release | NMDN_0975_ZMDN_4213 | Dusun Mual Bauge_Tarutung(I) | 2025-09-29 | 2 Days | 2025-09-30 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.3 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0975_ZMDN_4213 | Closed_Cek TERM 1
| 64 | 2025-09-23 | Waiting Release | NMDN_0977_NMDN_0486 | Sitampurung_PAGARAN | 2025-10-02 | 1 Days | 2025-10-02 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 1/2 Hop | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0977_NMDN_0486 | Closed_Cek TERM 1
| 65 | 2025-09-23 | Waiting Release | NMDN_0978_NMDN_0179 | Silangit_Muara(HUB19)(I) | 2025-09-30 | 2 Days | 2025-09-30 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0978_NMDN_0179 | Closed_Cek TERM 1
| 66 | 2025-09-23 | S1ID2025042515WBF1-16 | ZMDN_4740_SUM-SU-SDK-1235 | Kuta Padang_SIDIKALANG2 | 2025-10-14 | 2 Days | 2025-10-15 | 2 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-22 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-SDK-2793_SUM-SU-SDK-1235 | Closed_TERM 3 |  |  |  |  | Need Submit DR Upload & Open Task PAC
| 67 | 2025-09-23 | Waiting Release | ZMDN_4973_NMDN_0060 | Totopan(Shub)(K)_Laguboti(Shub)(K)(G) | 2025-10-11 | 2 Days | 2025-10-12 | 2 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4973_SUM-SU-BLG-1677 | L1 Approved |  |  | Doc Submit_Bayu | Dismantle
| 68 | 2025-09-23 | S1ID2025042515WBF1-57 | SUM-SU-BLG-0029_ZMDN_4973 | Tangga_Tangga batu repiter | 2025-10-09 | 2 Days | 2025-10-10 | 2 Days |  |  | ADIONO | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Inbound Done | Rejected | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-BLG-0029_ZMDN_4973 | Rejected
| 69 | 2025-09-19 | S1ID2025042515WBF1-12 | SUM-AC-JTH-0549_SUM-AC-SAB-0473 | Gampong Baru Aceh Besar TImur_Anoi Hitam Sabang | 2025-09-28 | 6 Days | 2025-10-06 | 8 Days | Site SD ant MW 1.2 dan 1.8 m |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade Main 1.8m, SD 1.2m | Nanggroe Aceh | North Sumatra | 350000190009 | I&C-Seperate MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Outbound Done | Rejected | Done | 400000 | 2025-10-27 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-JTH-0549_SUM-AC-SAB-0473 | Need Revise |  | Bayu | MW Agregate performance kurang bagus_need cek ZTE | MW
| 70 | 2025-09-19 | S1ID2025042515WBF1-12 | SUM-AC-JTH-0549_SUM-AC-SAB-0473 | Gampong Baru Aceh Besar TImur_Anoi Hitam Sabang | 2025-09-28 | 6 Days | 2025-10-06 | 8 Days | Site SD ant MW 1.2 dan 1.8 m |  | VALDINO RAWUNG | Swap Upgrade | Swap Upgrade Main 1.8m, SD 1.2m | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2025-10-27 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-JTH-0549_SUM-AC-SAB-0473 | N/A
Perlu revisi PO | 71 | 2025-10-06 | S1ID2025042515WBF1-57 (need Revisi) | SUM-AC-JTH-0549_SUM-AC-SAB-0473 | Gampong Baru Aceh Besar TImur_Anoi Hitam Sabang | 2025-10-08 | 3 Days | 2025-10-09 | 2 Days |  |  | VALDINO RAWUNG | Dismantle MW Keep | Dismantle SD 1.2 dan 1.8m | Nanggroe Aceh | North Sumatra | 350000190032 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna(SD) 4 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress | Kenapa Revisi PO. DUID di temukan di beberapa MW dismantle( po 413 ungu). Po no 413 nilai nya lenbih kecil ; actual antenna size 2 pcs 1.2m & 2 pcs 1.8m | 1000000 | 0 |  | SUM-AC-JTH-0549_SUM-AC-SAB-0473 | Closed_Cek Rev PO
| 72 | 2025-09-20 | S1ID2025042515WBF1-57 | NMDN_0959_SUM-SU-AKK-1131 | STO RANTAU PRAPAT_Perdamaian | 2025-09-25 | 2 Days | 2025-10-02 | 8 Days | NE blocking accesss STO Telkom(issue permit accsess STO) |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.3 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0959_SUM-SU-AKK-1131 | Closed_Cek TERM 1
| 73 | 2025-09-20 | S1ID2025042515WBF1-16 | SUM-SU-KPI-2428_SUM-SU-KPI-1151 | Labuhanbatu Selatan Sungai Kanan_Sungai Kanan | 2025-09-28 | 2 Days | 2024-09-28 | 1 Days | 1/2 HOP |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-16 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-KPI-2428_SUM-SU-KPI-1151 | Reject_Term 10% Submit |  |  |  |  | Reject_Term 10% Submit
| 74 | 2025-10-09 | S1ID2025042515WBF1-16 | ZMDN_5412_SUM-SU-PMS-0906 | Simpang_Dalik_Raya_RAYA_SIMALUNGUN | 2025-10-10 | 2 Days | 2025-10-10 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.9 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-16 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | ZMDN_5412_SUM-SU-PMS-0906 | L1 Approved
| 75 | 2025-10-12 | Waiting Release | ZMDN_4021_ZMDN_4896 |  | Week 2 October 25 | 2 Days |  |  |  |  | ADIONO | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Not Yet Start | Not Yet Start | Not Yet Start | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4021_ZMDN_4896 | Not Yet Start_Need PO
| 76 | 2025-10-12 | S1ID2025042515WBF1-16 | NMDN_0119_SUM-SU-KIS-0147 | _Aek Loba Pekan | 2025-10-14 | 2 Days | 2025-10-15 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-22 | Done | 100000 | 2026-01-21 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | NMDN_0119_SUM-SU-KIS-0147 | Closed
| 77 | 2025-10-12 | S1ID2025042515WBF1-28 | SUM-SU-KBJ-0121_SUM-SU-PMS-0898 | DOKAN_Seribu Dolok | Week 2 October 25 | 2 Days | Done |  |  | Material In HB | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-KBJ-0121_SUM-SU-PMS-0898 | Closed_Reject_Term 10%
| 78 | 2025-10-12 | S1ID2025042515WBF1-33 | SUM-SU-PMS-0928_SUM-SU-PMS-0942 | PANOMBEAN_Kartini Siantar | 2025-12-12 | 2 Days | 2025-12-28 | 16 Days | issue access | Material In HB | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-PMS-0928_SUM-SU-PMS-0942 | Closed
| 79 | 2025-10-09 | S1ID2025042515WBF1-13 | SUM-AC-LSK-0023_SUM-AC-LSK-0142 | ALUE LEUHOB_Cot Girek | 2025-10-17 | 4 Days | 2025-10-24 | 4 Days | Hujan |  | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-LSK-0023_SUM-AC-LSK-0142 | L1 Approved |  |  | Resubmit Doc done_Khairul | MW
| 80 | 2025-10-09 | S1ID2025042515WBF1-13 | SUM-AC-STR-0027_SUM-AC-STR-0206 | PAYA KARANG_Blangrakal | 2025-10-16 | 4 Days | 2025-11-01 | 7 Days | Hujan, OBU faulty |  | VALDINO RAWUNG | New Link | New Link 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Rejected | Done | 400000 | 2025-11-11 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-STR-0027_SUM-AC-STR-0206 | Need On Site |  |  | Need TS ODU | MW
| 81 | 2025-10-09 | S1ID2025042515WBF1-13 | SUM-AC-STR-0006_SUM-AC-TKN-0210 | WNOSOBO_Simpang Tritit | 2025-10-18 | 4 Days | 2025-10-28 | 6 Days | Hujan |  | RICARDO SINAGA | New Link | New Link 2+0_Ant MW 1.2 dan 0.9 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed with PL | Done | 400000 | 2025-11-11 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-STR-0006_SUM-AC-TKN-0210 | Need On Site |  |  |  | CPL
| 82 | 2025-10-09 | S1ID2025042515WBF1-13 | SUM-AC-STR-0018_SUM-AC-STR-0206 | NANTARA_Blangrakal | 2025-10-16 | 4 Days | 2025-10-30 | 6 Days | Hujan |  | RICARDO SINAGA | New Link | New Link 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2025-11-11 | Done | 500000 | 2026-02-24 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-STR-0018_SUM-AC-STR-0206 | Closed |  |  | Closed Doc | CPL
| 83 | 2025-10-09 | S1ID2025042515WBF1-13 | SUM-AC-STR-0022_SUM-AC-STR-0206 | RONGA_RONGA_Blangrakal | 2025-10-16 | 4 Days | 2025-10-30 | 7 Days | Hujan, ODU faulty |  | VALDINO RAWUNG | New Link | New Link 2+0_Ant MW 0.9 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-STR-0022_SUM-AC-STR-0206 | L1 Approved |  |  | Done Resubmit _Khairul | MW
| 84 | 2025-10-12 | Waiting Release | NACH_0026_NACH_0028 |  | Week 3 october 25 | 2 Days |  |  |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | Nanggroe Aceh | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Not Yet Start | Not Yet Start | Not Yet Start | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NACH_0026_NACH_0028 | Not Yet Start_Need PO
| 85 | 2025-10-12 | Waiting Release | NACH_0198_NACH_0051 |  | Week 3 october 25 | 2 Days |  |  |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | Nanggroe Aceh | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Not Yet Start | Not Yet Start | Not Yet Start | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NACH_0198_NACH_0051 | Not Yet Start_Need PO
| 86 | 2025-10-12 | S1ID2025042515WBF1-16 | NMDN_0882_SUM-SU-KIS-0157 | _Aek Loba Pekan | 2025-10-14 | 2 Days | 2025-10-15 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-22 | Done | 100000 | 2026-01-21 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | NMDN_0882_SUM-SU-KIS-0157 | Closed
| 87 | 2025-10-21 | S1ID2025042515WBF1-16 | ZMDN_4664_SUM-SU-LMP-0460 |  | 2025-10-26 | 2 Days | 2025-10-27 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-22 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-LMP-8230_SUM-SU-LMP-0460 | Closed_TERM 3 |  |  |  |  | Need Submit DR Upload & Open Task PAC
| 88 | 2025-10-21 | S1ID2025042515WBF1-57 | NMDN_0677_SUM-SU-KIS-1680 | Desa Sei Alim_Pulau Maria | 2025-10-23 | 2 Days | 2025-10-24 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  | 1000000 | 0 |  | NMDN_0677_SUM-SU-KIS-1680 | Closed_Cek TERM 1
| 89 | 2025-10-22 | S1ID2025042515WBF1-14 | SUM-AC-STR-0005_SUM-AC-TKN-0210 | SIMPANGTERETIET_Simpang Tritit | 2025-10-25 | 4 Days | 2025-10-28 | 4 Days |  |  | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2025-11-18 | Done | 500000 | 2026-02-24 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-STR-0005_SUM-AC-TKN-0210 | Closed_NEED OPEN TASK PAC
| 90 | 2025-10-24 | S1ID2025042515WBF1-17 | SUM-AC-LSK-0065_SUM-AC-LSK-0147 | ANTARA_NISAM | 2025-10-31 | 4 Days | 2025-11-04 | 4 Days |  |  | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2025-11-18 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-LSK-0065_SUM-AC-LSK-0147 | Closed_TERM 2 |  |  | Done Submit CPL by Bayu
| 91 | 2025-10-24 | S1ID2025042515WBF1-17 | SUM-AC-STR-0004_SUM-AC-STR-0215 | BENER_PEPANYI_Pondok baru | 2025-10-28 | 4 Days | 2025-10-30 | 4 Days |  |  | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed with PL | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-STR-0004_SUM-AC-STR-0215 | Team On Site | 10/05 Rectifikasi | Randi |  | CPL
| 92 | 2025-10-29 | S1ID2025042515WBF1-17 | SUM-AC-SGI-0021_SUM-AC-SGI-0692 | BS_GOGO_MESJID PEUDAYA | 2025-11-03 | 4 Days | 2025-11-15 | 12 Days | Recty BTS NY Ready |  | VALDINO RAWUNG | New Link | New Link 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed with PL | Done | 400000 | 2025-11-18 | Done | 500000 | 2025-01-07 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-SGI-0021_SUM-AC-SGI-0692 | Need On Site | 09/05 Randy_SGI-0692_Rektifikasi | Bayu | Need replace ODU RSL timpang -33dbm -36dbm | CPL | Need Open Task PAC
| 93 | 2025-10-26 | S1ID2025042515WBF1-16 | NMDN_0874_SUM-SU-LMP-0462 |  | 2025-10-27 | 2 Days | 2025-10-27 |  |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-22 | Done | 100000 | 2026-02-10 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | NMDN_0874_SUM-SU-LMP-0462 | Closed
| 94 | 2025-10-31 | S1ID2025042515WBF1-17 | SUM-AC-STR-0008_SUM-AC-STR-0382 | REMBELE_BUJANG_ACEH_TENGAH | 2025-11-05 | 4 Days | 2025-11-09 | 4 Days |  |  | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 0.9 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-STR-0008_SUM-AC-STR-0382 | Closed_TERM 1
| 95 | 2025-10-30 | S1ID2025042515WBF1-18 | SUM-AC-SGI-0005_SUM-AC-SGI-0429 | GEUNTENG_BARAT_BENTENG PIDIE | 2025-11-05 | 4 Days | 2025-11-17 | 12 Days | Recty BTS NY Ready |  | VALDINO RAWUNG | New Link | New Link 2+0_Ant MW 0.9 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed with PL | Done | 400000 | 2026-01-07 | Done | 500000 | 2026-02-24 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-SGI-0005_SUM-AC-SGI-0429 | In review ZTE |  |  | SGI-0429 doc CPL done share ke ZTE, SGI-0005 Plan Edit bayu | CPL
| 96 | 2025-10-30 | S1ID2025042515WBF1-17 | SUM-AC-MRN-0005_SUM-AC-MRN-0522 | TEUMANAH_MURNI_REUSEB | 2025-11-04 | 4 Days | Done |  | Recty BTS NY Ready |  | RICARDO SINAGA | New Link | New Link 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-MRN-0005_SUM-AC-MRN-0522 | Closed_TERM 1
| 97 | 2025-10-02 | S1ID2025042515WBF1-16 | SUM-AC-KRB-2398_SUM-AC-KRB-0089 | KUALASINPANG_LINTANG_Kuala Simpang Kota | 2025-10-03 | 2 Days | 2025-10-04 | 2 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 0.3 | Nanggroe Aceh | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-16 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-KRB-2398_SUM-AC-KRB-0089 | Closed_TERM 3 |  |  |  |  | Need Submit DR Upload & Open Task PAC
| 98 | 2025-10-02 | S1ID2025042515WBF1-16 | SUM-AC-KRB-1312_SUM-AC-KRB-0085 | ALUR TANI SATU_TAMIANG HULU | 2025-10-04 | 2 Days | 2025-10-05 | 2 Days |  |  | ADIONO | Dismantle MW Keep | Dismantle MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-16 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-KRB-1312_SUM-AC-KRB-0085 | Closed_TERM 3 |  |  |  |  | Need Submit DR Upload & Open Task PAC
| 99 | 2025-11-05 | S1ID2025042515WBF1-18 | SUM-AC-STR-0025_SUM-AC-STR-0214 | KENAWAT_SIMPANG TIGA | 2025-11-09 | 4 Days | 2025-11-13 | 4 Days |  |  | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | L1 Approved | Done | 400000 | 2026-01-07 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-STR-0025_SUM-AC-STR-0214 | L1 Approved |  |  |  | MW
| 100 | 2025-11-06 | S1ID2025042515WBF1-17 | SUM-AC-LSK-0039_SUM-AC-LSK-0567 | BINTANG_HU_LHOKSUKON_Lhoksukon2 reloc | 2025-11-08 | 4 Days | 2025-11-13 | 5 Days | Team Issue, hanya dilanjut dg 3 org(Ricardo, Paris, Angga) |  | RICARDO SINAGA/ANGGA WIJAYA-ATP | New Link | New Link 2+0_Ant MW 0.9 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed with PL | Done | 400000 | 2025-11-18 | Done | 500000 | 2026-02-24 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-AC-LSK-0039_SUM-AC-LSK-0567 | Need On Site |  |  |  | CPL | Need Open Task PAC
| 101 | 2025-11-04 | Waiting Release | SUM-SU-AKK-2719_SUM-SU-AKK-1124 | AFDELING_II_RANTAUPRAPAT_RANTAU PRAPAT2 | 2025-11-04 | 2 Days | 2025-11-07 | 3 Days | Negociate Access With MS Area |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.8 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-AKK-2719_SUM-SU-AKK-1124 | Not Yet Submit |  |  | Need Cek Rega Bayu
| 102 | 2025-11-07 | S1ID2025042515WBF1-16 | SUM-SU-KPI-2423_SUM-SU-KPI-1145 | LABUHANBATU SELATAN_SILANGKITANG_Silangkitang | 2025-11-07 | 2 Days | 2025-11-08 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-22 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-KPI-2423_SUM-SU-KPI-1145 | Closed_TERM 3 |  |  |  |  | Need Submit DR Upload & Open Task PAC
| 103 | 2025-11-07 | S1ID2025042515WBF1-16 | SUM-SU-TJB-2211_SUM-SU-TJB-1414 | DATUK_BANDAR_PAHANG_Tanjung Balai 2 | 2025-11-09 | 2 Days | 2025-11-09 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-22 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-TJB-2211_SUM-SU-TJB-1414 | Closed_TERM 3 |  |  |  |  | Need Submit DR Upload & PAC
| 104 | 2025-11-07 | S1ID2025042515WBF1-16 | SUM-SU-TJB-0184_SUM-SU-TJB-1417 | SEI_NANGKA_Kapias Tengah | 2025-11-10 | 2 Days | 2025-11-10 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-22 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-TJB-0184_SUM-SU-TJB-1417 | Closed_TERM 3 |  |  |  |  | Need Submit DR Upload & Open Task PAC
Perlu revisi PO | 105 | 2025-11-10 | S1ID2025042515WBF1-39 (need Revisi) | SUM-SU-KIS-0136_SUM-SU-KIS-0157 | Gunung Melayu_Aek Loba | 2025-11-11 | 2 Days | 2025-11-13 | 3 Days | Aksess Limit |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.8 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress | PO di temukan di mo 252, nilai Po lebih kecil ; actual antenna size 1.8m | 3608418 | -2608418 |  | SUM-SU-KIS-0136_SUM-SU-KIS-0157 | Closed_Cek Rev PO
| 106 | 2025-11-12 | S1ID2025042515WBF1-18 | SUM-AC-JTH-0001_SUM-AC-JTH-0392 | BEÚRADEH_COT LÀMPOH SOH ACEH BESAR | 2025-11-14 | 4 Days | 2025-11-17 | 4 Days |  |  | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-01-07 | Done | 500000 | 2026-02-24 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-AC-JTH-0001_SUM-AC-JTH-0392 | Reject_Term 10% Submit
| 107 | 2025-11-14 | S1ID2025042515WBF1-20 | SUM-SU-AKK-1116_SUM-SU-AKK-0002 | SUKARAME BARU_Sei Piring | 2025-11-14 | 2 Days | 2025-11-14 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.8 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-AKK-1116_SUM-SU-AKK-0002 | Closed_NEED OPEN TASK PAC
| 108 | 2025-11-14 | S1ID2025042515WBF1-18 | SUM-AC-LSK-0042_SUM-AC-LSK-0260 | ayeuk Pange_TRIENG LSK SELATAN ACEH UTARA | 2025-11-19 | 4 Days | Done |  | 5 Hari full Hujan |  | VALDINO/ANGGA WIJAYA-ATP | New Link | New Link 2+0_Ant MW 0.9 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-LSK-0042_SUM-AC-LSK-0260 | Closed_Cek TERM 2
| 109 | 2025-11-14 | S1ID2025042515WBF1-18 | SUM-AC-LSK-0016_SUM-AC-LSK-0134 | PAYA LUENG_Paya Bakong | 2025-11-19 | 4 Days | Done |  | 5 Hari full Hujan |  | RICARDO SINAGA/ANGGA WIJAYA-ATP | New Link | New Link 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-01-07 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-LSK-0016_SUM-AC-LSK-0134 | Closed_Cek TERM 2
| 110 | 2025-11-14 | S1ID2025042515WBF1-18 | SUM-AC-STR-0030_SUM-AC-STR-0208 | LUT_KUCAK_Simpang Balek | 2025-11-20 | 4 Days | Done |  | Team Lanjut MOS JTH0004 Dan JTH 0006 | QSCK Reject, Watermark Photo Not Match with Iepms | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-STR-0030_SUM-AC-STR-0208 | Closed_Cek TERM 2
Perlu revisi PO | 111 | 2025-11-14 | S1ID2025042515WBF1-18 (need Revisi) | SUM-AC-STR-0010_SUM-AC-STR-0215 | BANDAR_SYIAH_UTAMA_Pondok baru | 2025-11-19 | 4 Days | Done |  | Team Lanjut MOS JTH0004 Dan JTH 0006 | Ny submit QSCK | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress | Perlu revisi PO karena di PO nilai lebih kecil ; diperlukan Revisi sub regional dari NS ke Nangro Aceh | 1000000 | 0 |  | SUM-AC-STR-0010_SUM-AC-STR-0215 | Closed_Cek Rev PO
Perlu revisi PO | 112 | 2025-11-14 | S1ID2025042515WBF1-18 (need Revisi) | SUM-AC-LSK-0041_SUM-AC-LSK-0132 | BUKIT_GELUMPANG_Meurah Mulia | 2025-11-19 | 4 Days | Done |  | 5 Hari full Hujan |  | VALDINO/ANGGA WIJAYA-ATP | New Link | New Link 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress | Data di sheet Rekap PO no 128 lebih kecil daripada di sheet ini ; diperlukan Revisi sub regional dari NS ke Nangro Aceh | 1000000 | 0 |  | SUM-AC-LSK-0041_SUM-AC-LSK-0132 | Closed_Cek Rev PO
| 113 | 2025-11-18 | S1ID2025042515WBF1-21 | SUM-AC-JTH-0006_SUM-AC-JTH-0069 | LHONG_1/Lhong Baru_Lhoong | 2025-11-25 | 4 Days | Done |  |  |  | ANGGA WIJAYA | Reroute | Reroute 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-JTH-0006_SUM-AC-JTH-0069 | Closed_Cek TERM 1
| 114 | 2025-11-18 | DI TAKE OVER | SUM-AC-STR-0017_SUM-AC-STR-0206 | Blangrakal | [5 empty] | MATERIAL RETURNED TO ZTE | NY ASSIGN TO TEAM | Reroute | Reroute 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 |  |  | Return to ZTE | Return to ZTE | Return to ZTE | [12 empty] | 0 | 0 | 0 | 0 | Di Take Over | ini di cabut dari TRU pekerjaannya dan di kasih ke partner lain |  |  |  | SUM-AC-STR-0017_SUM-AC-STR-0206 | Return to ZTE
Perlu revisi PO | 115 | 2025-11-18 | S1ID2025042515WBF1-21 (need Revisi) | SUM-AC-JTH-0004_SUM-AC-JTH-0079 | RABO 2_MEUNASAH_TUNONG_Seulimeum | 2025-11-24 | 4 Days | Done |  |  |  | ANGGA WIJAYA | Reroute | Reroute 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress | Kenapa Revisi PO. DUID di temukan (137), nilai di PO lebih kecil ; diperlukan Revisi sub regional dari NS ke Nangro Aceh | 1000000 | 0 |  | SUM-AC-JTH-0004_SUM-AC-JTH-0079 | Closed_Cek Rev PO
| 116 | 2025-11-14 | S1ID2025042515WBF1-20 | SUM-SU-TJB-0186_SUM-SU-TJB-1415 | Kapias Tengah_PANTAI BURUNG | 2025-11-15 | 2 Days | 2025-11-18 | 4 Days | 3 hari full hujan, team not onsite |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-TJB-0186_SUM-SU-TJB-1415 | Closed_NEED OPEN TASK PAC
| 117 | 2025-11-18 | S1ID2025042515WBF1-27 | SUM-AC-LSK-0058_SUM-AC-LSK-0139 | BAKTYA BARAT_Cot usen | 2026-01-05 | 4 Days | Done |  | Team continue MOS BIR 0030 | RFS DONE, NEED REPOINTING AND TAKE DATA | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | Done | 500000 |  | Done | 100000 | 2026-03-03 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | SUM-AC-LSK-0058_SUM-AC-LSK-0139 | Closed
| 118 | 2025-11-22 | S1ID2025042515WBF1-30 | SUM-AC-LSK-0033_SUM-AC-LSK-0132 | MEURAH_Meurah Mulia | 2025-12-15 | 4 Days | Done |  |  |  | VALDINO/ANGGA WIJAYA-ATP | Reroute | Reroute 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-LSK-0033_SUM-AC-LSK-0132 | Closed_Cek TERM 2
| 119 | 2025-11-22 | S1ID2025042515WBF1-22 | SUM-AC-LSM-0005_SUM-AC-LSK-0151 | JEULIKAT_Banda Masem | 2025-12-12 |  | Done |  |  |  | RUDI GUNAWAN/ANGGA WIJAYA-ATP | Reroute | Reroute 2+0_Ant MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-27 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-LSM-0005_SUM-AC-LSK-0151 | Closed_Cek TERM 2 |  |  | Done Submit CPL by Bayu
| 120 | 2025-11-24 | S1ID2025042515WBF1-30 | SUM-AC-LSK-0037_SUM-AC-LSM-0467 | SUKADAMAI DUO_DAYAH BARO LHOKSUMAWE | 2025-12-12 |  | Done |  |  | Access Issue | VALDINO/ANGGA WIJAYA-ATP | New Link | New Link 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-LSK-0037_SUM-AC-LSM-0467 | Closed_Cek TERM 2
| 121 | 2025-11-24 | S1ID2025042515WBF1-30 | SUM-AC-LSK-0021_SUM-AC-LGS-2326 | LANGKAHAN_DUO_BUKET_BATA_PANTE_BIDARI | 2025-12-12 |  | Done |  |  | Waiting Recovery BTS | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 1.8 dan 1.2 | Nanggroe Aceh | North Sumatra | 350000190004 | I&C-Seperate MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Outbound Done | Need Revise | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-LSK-0021_SUM-AC-LGS-2326 | Need Revise |  | Bayu | Need Revise_Bayu | MW
| 122 | 2025-11-24 | S1ID2025042515WBF1-40 | SUM-AC-KRB-0012_SUM-AC-KRB-1309 | DUSUN SIDOMULYA_SEUMADAM ACEH TIMUR | 2026-01-12 | 4 Days | Done |  |  | Access Issue | FERNANDO | New Link | New Link 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Rejected | Done | 400000 | 2026-02-27 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-KRB-0012_SUM-AC-KRB-1309 | In review ZTE | 09/05 Dedek/Rinaldi_Rev Reject ATP | Bayu | Team on site rektifikasi_Team Dedek Anggara Doc Resubmit_Bayu | MW
| 123 | 2025-11-24 | S1ID2025042515WBF1-42 | SUM-AC-KRB-0027_SUM-AC-KRB-0085 | SUNTING_Tamiang Hulu | 2025-11-25 | 4 Days | Done | 63 Days | site area bencana banjir aceh | Access Issue | FERNANDO | New Link | New Link 2+0_Ant MW 1.8 dan 1.2 | Nanggroe Aceh | North Sumatra | 350000190004 | I&C-Seperate MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-KRB-0027_SUM-AC-KRB-0085 | Not Yet Submit |  | Bayu | Done cek data team Randi 07/05 | MW
| 124 | 2025-11-10 | S1ID2025042515WBF1-16 | ZMDN_4595_SUM-SU-KIS-0151 | AIR BATU 2_AIR BATU | 2025-11-14 | 2 Days | 2025-11-14 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2025-12-08 | Done | 500000 | 2025-12-22 | Done | 100000 | 2026-02-27 |  |  |  | 1000000 | 0 | 1000000 | 0 | Done |  |  |  |  | ZMDN_4595_SUM-SU-KIS-0151 | Closed
| 125 | 2025-11-10 | S1ID2025042515WBF1-28 | SUM-SU-KIS-2227_SUM-SU-KIS-0173 | HESSA_AIR_GENTING_Sei Alim Hasik | 2025-11-19 | 2 Days | 2025-11-19 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-KIS-2227_SUM-SU-KIS-0173 | Reject_Term 10% Submit
| 126 | 2025-11-10 | S1ID2025042515WBF1-35 | SUM-SU-AKK-2251_SUM-SU-AKK-0003 | Gunung Melayu_Siamporik | 2025-11-22 | 2 Days | 2025-11-22 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | Done | 100000 | 2026-04-29 |  |  |  | 1000000 | 0 | 1000000 | 0 | In Progress |  |  |  |  | SUM-SU-AKK-2251_SUM-SU-AKK-0003 | Term 10% Approve
| 127 | 2025-11-10 | S1ID2025042515WBF1-28 | SUM-SU-AKK-2253_SUM-SU-AKK-1111 | Bandar Lama_Damule Pekan | 2025-11-22 | 2 Days | 2025-11-22 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-AKK-2253_SUM-SU-AKK-1111 | Reject_Term 10% Submit
| 128 | 2025-12-01 | S1ID2025042515WBF1-21 | ZMDN_4840_SUM-SU-SRH-1289 | IBSKampung Pon_Sungai Rampah | 2025-12-04 |  | Done |  |  |  | ADIONO | Reroute | Reroute 2+0_Ant MW 0.6 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2025-12-22 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_4840_SUM-SU-SRH-1289 | Closed_Cek TERM 2
| 129 | 2025-12-01 | S1ID2025042515WBF1-21 | ZMDN_4840_SUM-SU-SRH-1289 | IBSKampung Pon_Sungai Rampah | 2025-12-04 | [5 empty] | ADIONO | Reroute | Reroute 2+0_Ant MW 0.6 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2025-12-22 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_4840_SUM-SU-SRH-1289 | N/A
| 130 | 2025-12-01 | S1ID2025042515WBF1-53 | ZMDN_4618_SUM-SU-LMP-0479 | ZMDN_4618_Pahang | 2025-12-05 |  | Done |  |  |  | ANGGA WIJAYA | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4618_SUM-SU-LMP-0479 | Closed_Cek TERM 1
| 131 | 2025-12-01 | S1ID2025042515WBF1-53 | ZMDN_4618_SUM-SU-LMP-0479 | ZMDN_4618_Pahang | 2025-12-05 | [5 empty] | ANGGA WIJAYA | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4618_SUM-SU-LMP-0479 | N/A
| 132 | 2025-12-01 | S1ID2025042515WBF1-22 | ZMDN_5322_SUM-SU-LMP-0469 | SF-ZMDN_5322-LIMAPULUH_Lima Puluh | 2025-12-04 |  | Done |  |  |  | RUDI GUNAWAN | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-01-07 | Done | 500000 | 2026-02-27 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | ZMDN_5322_SUM-SU-LMP-0469 | Closed_NEED OPEN TASK PAC
| 133 | 2025-12-01 | S1ID2025042515WBF1-22 | ZMDN_5322_SUM-SU-LMP-0469 | SF-ZMDN_5322-LIMAPULUH_Lima Puluh | 2025-12-04 | [5 empty] | RUDI GUNAWAN | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2026-01-07 | Done | 500000 | 2026-02-27 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | ZMDN_5322_SUM-SU-LMP-0469 | N/A
| 134 | 2025-12-05 | S1ID2025042515WBF1-23 | SUM-AC-LSK-0031_SUM-AC-LSK-0561 | BLANG_POHROH_BLANG_DALAM_TUNONG | 2025-12-16 | 4 Days | 2025-12-20 | 4 Days |  |  | RUDI GUNAWAN | New Link | New Link 2+0_Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed with PL | Done | 400000 | 2026-01-07 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-LSK-0031_SUM-AC-LSK-0561 | Need On Site |  |  |  | CPL
| 135 | 2025-12-05 | DI TAKE OVER | SUM-AC-STR-0019_SUM-AC-STR-0214 | [6 empty] | Hold, outbound(Access Issue) | NY ASSIGN TO TEAM | New Link | New Link 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 |  |  | Return to ZTE | Return to ZTE | Return to ZTE | [12 empty] | 0 | 0 | 0 | 0 | Di Take Over | ini di cabut dari TRU pekerjaannya dan di kasih ke partner lain |  |  |  | SUM-AC-STR-0019_SUM-AC-STR-0214 | Return to ZTE
| 136 | 2025-12-05 | S1ID2025042515WBF1-29 | SUM-AC-BIR-0030_SUM-AC-BIR-0374 | TAMTA_COT KEURANJI BIREUEN | 2026-01-10 | 4 Days | Done |  |  | EHS Done, QSCK waiting review | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-BIR-0030_SUM-AC-BIR-0374 | Closed_Cek TERM 2
| 137 | 2025-12-08 | S1ID2025042515WBF1-22 | SUM-SU-PMS-0039_SUM-SU-PMS-0913 | SONDI_RAYA_Pane | 2025-12-10 | 4 Days | Done |  | Issue U Bold tidak pass, clear 2 hari kemudian |  | RICARDO SINAGA | New Link | New Link 2+0_Ant MW 1.2 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-01-07 | Done | 500000 | 2026-02-27 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-PMS-0039_SUM-SU-PMS-0913 | Reject_Term 10% Submit
| 138 | 2025-12-04 | S1ID2025042515WBF1-31 | SUM-SU-KIS-2229_SUM-SU-KIS-0156 | KELURAHAN SIUMBUT UMBUT_MERANTI ASAHAN | 2025-12-08 | 1 Days | 2025-12-08 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | Done | 100000 | 2026-04-29 |  |  |  | 1000000 | 0 | 1000000 | 0 | In Progress |  |  |  |  | SUM-SU-KIS-2229_SUM-SU-KIS-0156 | Term 10% Approve
| 139 | 2025-12-08 | S1ID2025042515WBF1-28 | SUM-SU-AKK-2248_SUM-SU-AKK-0163 | KUALUH SELATAN TANJUNG PASIR_Aek Kanopan | 2025-12-08 | 1 Days | 2025-12-09 | 2 Days | Team Sick |  | TEAM EXTERNAL | Dismantle MW Keep | Ant MW 1.8 dan 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-AKK-2248_SUM-SU-AKK-0163 | Reject_Term 10% Submit
Perlu revisi PO | 140 | 2025-12-02 | S1ID2025042515WBF1-28 (need Revisi) | SUM-SU-AKK-2255_SUM-SU-AKK-1117 | BANGUN_REJO _KAMPUNG PAJAK | 2025-12-02 | 1 Days | 2025-12-02 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | DI PO no 182 di sheet Rekap PO, nilai Po lebih kecil dari nilai di sini ; Diperlukan revisi PO actual size antenna 2 pcs 1.2m | 1000000 | 0 |  | SUM-SU-AKK-2255_SUM-SU-AKK-1117 | Reject_Term 10% Submit
| 141 | 2025-12-09 | S1ID2025042515WBF1-28 | SUM-SU-KBJ-2234_SUM-SU-KBJ-0121 | MULIA_RAYAT_DOKAN | 2025-12-09 | 1 Days | 2025-12-09 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-KBJ-2234_SUM-SU-KBJ-0121 | L1 Approved_Reject_Term 10%
| 142 | 2025-12-14 | S1ID2025042515WBF1-31 | SUM-SU-KBJ-0103_SUM-SU-KBJ-0096 | Berastagi 2_Barangkersap | 2025-12-16 | 1 Days | 2025-12-16 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-KBJ-0103_SUM-SU-KBJ-0096 | Closed
| 143 | 2025-12-14 | S1ID2025042515WBF1-28 | SUM-SU-KBJ-2652_SUM-SU-KBJ-0103 | RUMAH BRASTAGI_BERASTAGI 2 | 2025-12-14 | 2 Days | 2025-12-15 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-KBJ-2652_SUM-SU-KBJ-0103 | L1 Approved_Reject_Term 10%
| 144 | 2025-12-06 | S1ID2025042515WBF1-35 | SUM-SU-AKK-1537_SUM-SU-AKK-1141 | 3227585G9_3G_PERS_SIDOREJO_LABUHAN_BATU_Rantau Prapat Timur | 2025-12-06 | 1 Days | 2025-12-16 | 10 Days | Team change plan other site cause in location always bad weather |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | Done | 100000 | 2026-04-29 |  |  |  | 1000000 | 0 | 1000000 | 0 | In Progress |  |  |  |  | SUM-SU-AKK-1537_SUM-SU-AKK-1141 | Term 10% Approve
| 145 | 2015-12-15 | S1ID2025042515WBF1-28 | SUM-SU-KBJ-0070_SUM-SU-KBJ-0072 | Mardinding_PERBULAN KARO | 2025-12-18 | 2 Days | 2025-12-18 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-KBJ-0070_SUM-SU-KBJ-0072 | L1 Approved_Reject_Term 10%
| 146 | 2015-12-15 | S1ID2025042515WBF1-28 | SUM-SU-KBJ-0072_SUM-SU-KBJ-0074 | PERBULAN KARO_Kinangkong | 2025-12-18 | 2 Days | 2025-12-19 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-KBJ-0072_SUM-SU-KBJ-0074 | L1 Approved_Reject_Term 10%
| 147 | 2025-12-20 | S1ID2025042515WBF1-34 | SUM-SU-PMS-0033_SUM-SU-PMS-0909 | BANDAR MARUHUR_Silau Kahean | 2025-12-23 | 4 Days | Done |  |  | Ny submit QSCK | TEAM EXTERNAL | New Link | New Link 2+0_Ant MW 1.2 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-27 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-PMS-0033_SUM-SU-PMS-0909 | Closed_Cek TERM 2
| 148 | 2025-12-15 | S1ID2025042515WBF1-24 | SUM-SU-DLS-0016_SUM-SU-TRT-1424 | HUTASOITII_Pagaran | 2025-12-20 | 4 Days | Done |  |  | QSCK Reject, Need retake part photo | RICARDO SINAGA | New Link | New Link 2+0_Ant MW 1.2 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | In review ZTE | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-DLS-0016_SUM-SU-TRT-1424 | In review ZTE | 09/05 Doc resubmit | Khairul | Reject still single nut, NY Double Nut | MW
| 149 | 2025-12-15 | S1ID2025042515WBF1-36 | SUM-SU-PMS-0031_SUM-SU-KIS-2129 | SIMPANGPETE_SEI SILAU BARAT | 2005-12-20 | 4 Days | Done |  |  | Ny submit QSCK | RICARDO SINAGA | New Link | New Link 2+0_Ant MW 1.2 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-27 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-PMS-0031_SUM-SU-KIS-2129 | Closed_Cek TERM 2
| 150 | 2025-12-16 | S1ID2025042515WBF1-26 | SUM-AC-LSK-0017_SUM-AC-LSK-0145 | LHOK_PUUK_Seunodon | 2025-12-18 | 4 Days | Done |  |  | EHS Done, QSCK Reject, BTS Near End NY install | ANGGA WIJAYA | New Link | New Link 2+0_Ant MW 0.9 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-LSK-0017_SUM-AC-LSK-0145 | Closed_Cek TERM 2
| 151 | 2025-08-28 | S1ID2025042515WBF1-5 | SUM-SU-AKK-1678_SUM-SU-AKK-0008 | Tanjung Ledong_SIMANDULANG LABUHAN BATU | 2025-12-27 | 2 Days | 2025-12-27 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-01-07 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Reject_Term 10% Submit_change PIC to Wang Guan Lun10328092 |  |  |  | SUM-SU-AKK-1678_SUM-SU-AKK-0008 | Reject_Term 10% Submit
| 152 |  | S1ID2025042515WBF1-31 | ZMDN_5322_SUM-SU-LMP-0469 | Baturaden_Lima Puluh | 2025-12-26 | 2 Days | Done |  | NE site STO, permit STO NY released | Done Dismantle 1/2 Hop, Material 1/2 Hop already in HB | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0,6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | ZMDN_5322_SUM-SU-LMP-0469 | Closed_NEED OPEN TASK PAC
| 153 | 2015-12-15 | S1ID2025042515WBF1-31 | SUM-SU-KBJ-0091_SUM-SU-KBJ-0096 | Sukandebi_Barangkersap | 2025-12-27 | 2 Days | 2025-12-27 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-KBJ-0091_SUM-SU-KBJ-0096 | Closed_Cek TERM 2
| 154 | 2026-12-26 | S1ID2025042515WBF1-31 | SUM-SU-PMS-2637_SUM-SU-PMS-0952 | Siantar Plaza - Shopping mall_3026_PEMATANG SIANTAR2 | 2025-12-30 | 2 Days | 2025-12-30 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0,6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-PMS-2637_SUM-SU-PMS-0952 | Closed_NEED OPEN TASK PAC
| 155 | 2026-01-06 | S1ID2025042515WBF1-31 | ZMDN_4836_SUM-SU-PMS-1521 | IBSTanah Jawa_PEMATANG TANAH JAWA SIMALUNGUN | 2025-12-30 | 2 Days | 2025-12-31 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0,6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | Done | 100000 | 2026-04-29 |  |  |  | 1000000 | 0 | 1000000 | 0 | In Progress |  |  |  |  | ZMDN_4836_SUM-SU-PMS-1521 | Term 10% Approve
| 156 | 2026-01-02 | S1ID2025042515WBF1-30 | NMDN_0034_SUM-SU-LBP-0411 | IBS Gang Turi_Perdamean Tanjung Morawa | 2026-01-07 | 4 Days | Done |  | Permit late released | pending Take Data, Issue akcess vandalisme kabel power BTS | ADIONO/RICARDO SINAGA-ATP | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | L1 Approved | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0034_SUM-SU-LBP-0411 | L1 Approved |  |  | Doc resubmit done_Bayu | MW
| 157 | 2026-01-02 | S1ID2025042515WBF1-30 | NMDN_0034_SUM-SU-LBP-0411 | IBS Gang Turi_Perdamean Tanjung Morawa | 2026-01-07 | 4 Days | Done |  | Permit late released | Done RFS, waiting plan take data | ADIONO/RICARDO SINAGA-ATP | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0034_SUM-SU-LBP-0411 | N/A
| 158 | 2026-01-02 | S1ID2025042515WBF1-30 | NMDN_0739_SUM-SU-LBP-0227 | SF-NMDN_0739-Puji Mulio_3G Sei Semayang Timur | 2026-01-08 | 4 Days | Done |  |  | EHS Done, QSCK not yet submit | RUDI GUNAWAN | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0739_SUM-SU-LBP-0227 | Closed_Cek TERM 2
| 159 | 2026-01-02 | S1ID2025042515WBF1-30 | NMDN_0739_SUM-SU-LBP-0227 | SF-NMDN_0739-Puji Mulio_3G Sei Semayang Timur | 2026-01-08 | 4 Days |  |  |  | EHS Done, QSCK not yet submit | RUDI GUNAWAN | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0739_SUM-SU-LBP-0227 | N/A
| 160 | 2026-01-02 | S1ID2025042515WBF1-30 | NMDN_0707_SUM-SU-LBP-0308 | SF-NMDN_0707-Jl Satria_Mekarsari Marendal | 2026-01-10 | 4 Days | Done |  |  |  | RICARDO SINAGA | Reroute | Reroute 2+0_Ant MW 0.6 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | L1 Approved | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0707_SUM-SU-LBP-0308 | L1 Approved |  |  |  | MW
| 161 | 2026-01-02 | S1ID2025042515WBF1-30 | NMDN_0707_SUM-SU-LBP-0308 | SF-NMDN_0707-Jl Satria_Mekarsari Marendal | 2026-01-10 | 4 Days |  |  |  |  | RICARDO SINAGA | Reroute | Reroute 2+0_Ant MW 0.6 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0707_SUM-SU-LBP-0308 | N/A
| 162 | 2026-01-02 | S1ID2025042515WBF1-36 | NMDN_0746_SUM-SU-LBP-0367 | SF-NMDN_0746-Dusun X Amal Bakti_Pasar V Tembung | 2026-01-08 | 4 Days | Done |  |  | EHS Done, QSCK not yet submit | RICARDO SINAGA | Reroute | Reroute 2+0_Ant MW 0.6 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | L1 Approved | Done | 400000 | 2026-02-27 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0746_SUM-SU-LBP-0367 | L1 Approved |  |  | Resubmit Doc done_Khairul | MW
| 163 | 2026-01-02 | S1ID2025042515WBF1-36 | NMDN_0746_SUM-SU-LBP-0367 | SF-NMDN_0746-Dusun X Amal Bakti_Pasar V Tembung | 2026-01-08 | 4 Days |  |  |  | EHS Done, QSCK not yet submit | RICARDO SINAGA | Reroute | Reroute 2+0_Ant MW 0.6 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2026-02-27 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0746_SUM-SU-LBP-0367 | N/A
| 164 | 2026-01-02 | S1ID2025042515WBF1-30 | NMDN_0402_SUM-SU-LBP-0505 | Sukadono_Tanjung Gusta | 2026-01-10 | 4 Days | Done |  |  | EHS Done, QSCK not yet submit | RUDI GUNAWAN | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0402_SUM-SU-LBP-0505 | Closed_Cek TERM 2
| 165 | 2026-01-02 | S1ID2025042515WBF1-30 | NMDN_0402_SUM-SU-LBP-0505 | Sukadono_Tanjung Gusta | 2026-01-10 | 4 Days |  |  |  | EHS Done, QSCK not yet submit | RUDI GUNAWAN | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0402_SUM-SU-LBP-0505 | N/A
| 166 | 2026-01-02 | S1ID2025042515WBF1-41 | ZMDN_4118_SUM-SU-LBP-0338 | IBS MEDAN ESTATE_LAUT DENDANG | 2026-01-11 | 4 Days | Done |  |  | EHS Done, QSCK not yet submit | ADIONO/RICARDO SINAGA-ATP | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2036-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_4118_SUM-SU-LBP-0338 | Closed_Cek TERM 2
| 167 | 2026-01-02 | S1ID2025042515WBF1-41 | ZMDN_4118_SUM-SU-LBP-0338 | IBS MEDAN ESTATE_LAUT DENDANG | 2026-01-11 | 4 Days |  |  |  | EHS Done, QSCK not yet submit | ADIONO/RICARDO SINAGA-ATP | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2036-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_4118_SUM-SU-LBP-0338 | N/A
| 168 | 2026-01-02 | S1ID2025042515WBF1-33 | SUM-SU-AKK-2444_SUM-SU-AKK-1119 | LABUHANBATU UTARA_NA IX-X_NA IX-X | 2026-01-07 | 2 Days | 2026-01-08 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-AKK-2444_SUM-SU-AKK-1119 | Closed_Cek TERM 2
| 169 | 2026-01-02 | S1ID2025042515WBF1-31 | SUM-SU-AKK-2138_SUM-SU-AKK-1168 | TELUK PIAI_Tanjung Sarang Elang | 2026-01-15 | 2 Days | 2026-01-16 | 2 Days |  | Hard Access | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-AKK-2138_SUM-SU-AKK-1168 | Closed_NEED OPEN TASK PAC
| 170 | 2026-01-06 | S1ID2025042515WBF1-31 | SUM-SU-AKK-2208_SUM-SU-AKK-1157 | KAMPUNG_PADANG_Kampung Sennah | 2026-01-21 | 2 Days | 2026-01-21 | 1 Days |  | Hard Access | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.8 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | Done | 100000 | 2026-04-29 |  |  |  | 1000000 | 0 | 1000000 | 0 | In Progress |  |  |  |  | SUM-SU-AKK-2208_SUM-SU-AKK-1157 | Term 10% Approve
| 171 | 2026-01-06 | S1ID2025042515WBF1-33 | ZMDN_4618_SUM-SU-LMP-0479 | Labuhan Ruku_Desa Pahang | 2026-01-10 | 2 Days | 2026-01-12 | 3 Days | Permit NE late released | Fe Done, NE waiting permit released | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0,6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_4618_SUM-SU-LMP-0479 | Closed_Cek TERM 2
| 172 | 2026-01-06 | S1ID2025042515WBF1-31 | ZMDN_5346_SUM-SU-LMP-0474 | Batubara_Petatal(I) | 2026-01-10 | 2 Days | 2026-01-11 | 2 Days | permit FE not yet released | NE Done, FE waiting permit released | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | ZMDN_5346_SUM-SU-LMP-0474 | Closed_NEED OPEN TASK PAC
| 173 | 2026-01-02 | S1ID2025042515WBF1-31 | SUM-SU-TRT-2014_SUM-SU-TRT-1428 | SITABOTABO_2222569_Paniaran | 2026-01-06 | 2 Days | 2026-01-06 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | DSM ANT 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-TRT-2014_SUM-SU-TRT-1428 | L1 Approved
| 174 | 2026-01-02 | S1ID2025042515WBF1-31 | SUM-SU-TRT-2016_SUM-SU-TRT-1432 | LOBU_SIREGAR_II_Pohan Tongah | 2026-01-07 | 2 Days | 2026-01-07 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | DSM ANT 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-TRT-2016_SUM-SU-TRT-1432 | L1 Approved
| 175 | 2026-01-02 | S1ID2025042515WBF1-47 | SUM-SU-TRT-1442_SUM-SU-TRT-1430 | PANGARIBUAN_Siborong-borong | 2026-01-08 | 2 Days | Done |  | permit FE not yet released | NE Done, FE waiting permit released | TEAM EXTERNAL | Dismantle MW Keep | DSM ANT 2.4 | North Sumatra | North Sumatra | 350000190028 | Dismantling&Simple Packing: MW+2.0-3.2m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-04-13 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-TRT-1442_SUM-SU-TRT-1430 | Closed_Cek TERM 2
Perlu revisi PO | 176 | 2026-01-06 | S1ID2025042515WBF1-31 (need Revisi) | SUM-SU-PMS-0911_SUM-SU-PMS-0935 | SONDI_RAYA_Site Tiga Balata | 2026-01-11 | 2 Days | 2026-01-11 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.8 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress | Nilai di Po no 212, lebih kecil dari nilai yg di sini ; Diperlukan revisi PO actual 2 pcs size antenna 1.8m | 1000000 | 0 |  | SUM-SU-PMS-0911_SUM-SU-PMS-0935 | L1 Approved |  |  | 0605 Approver reject, Dokumen Matra tidak tersedia 0705 Doc Submit | Dismantle
| 177 | 2026-01-06 | S1ID2025042515WBF1-31 | SUM-SU-PMS-0918_SUM-SU-PMS-0962 | RAYA KAHEAN_Site Dolok Merangir | 2026-01-14 | 2 Days | 2026-01-15 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.8 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | Done | 100000 | 2026-04-29 |  |  |  | 1000000 | 0 | 1000000 | 0 | In Progress |  |  |  |  | SUM-SU-PMS-0918_SUM-SU-PMS-0962 | Term 10% Approve
| 178 | 2026-01-06 | S1ID2025042515WBF1-31 | SUM-SU-SRH-1266_SUM-SU-SRH-0965 | Serbananti_Site Dolok Merangir | 2026-01-14 | 2 Days | 2026-01-15 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Rejected | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-SRH-1266_SUM-SU-SRH-0965 | Rejected
| 179 | 2026-01-06 | S1ID2025042515WBF1-31 | SUM-SU-SRH-1273_SUM-SU-PMS-0962 | Marjanji_Site Dolok Merangir | 2026-01-15 | 2 Days | 2026-01-16 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | Done | 100000 | 2026-04-29 |  |  |  | 1000000 | 0 | 1000000 | 0 | In Progress |  |  |  |  | SUM-SU-SRH-1273_SUM-SU-PMS-0962 | Term 10% Approve
| 180 | 2026-01-16 | S1ID2025042515WBF1-45 | NMDN_0517_SUM-SU-PSP-1217 | IBS_Phase 4C_2483_NSM_ANGGOLI TAPSEL | 2026-01-26 | 4 Days | 2026-01-31 | 6 Days |  |  | RUDI GUNAWAN | Reroute | Reroute 2+0_Ant MW 1.2 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0517_SUM-SU-PSP-1217 | Closed_Cek TERM 1
| 181 | 2026-01-16 | S1ID2025042515WBF1-45 | NMDN_0517_SUM-SU-PSP-1217 | IBS_Phase 4C_2483_NSM_ANGGOLI TAPSEL | 2026-01-26 | 4 Days | 2026-01-31 | 6 Days |  |  | RUDI GUNAWAN | Reroute | Reroute 2+0_Ant MW 1.2 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0517_SUM-SU-PSP-1217 | N/A
| 182 | 2026-01-17 | S1ID2025042515WBF1-36 | ZMDN_4944_SUM-SU-MDN-0573 | MC-Johor6_2223183_EkaBudiMedan | 2026-01-24 | 4 Days | Done |  | material broken |  | FERNANDO | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4944_SUM-SU-MDN-0573 | Not Yet Submit | 09/05 Benny_MDN-0573_take data | Bayu | FE site SUM-SU-MDN-0573 info TP Clear block access 0705 Team Benny on site | MW
| 183 | 2026-01-17 | S1ID2025042515WBF1-36 | ZMDN_4944_SUM-SU-MDN-0573 | MC-Johor6_2223183_EkaBudiMedan | 2026-01-24 | 4 Days |  |  | material broken |  | FERNANDO | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4944_SUM-SU-MDN-0573 | N/A
| 184 | 2026-01-17 | S1ID2025042515WBF1-41 | ZMDN_5327_SUM-SU-MDN-0299 | Danau Singkarak GMT_3G MC PABRIK TINUN PETISAH | 2026-01-22 | 4 Days | 2026-01-24 | 3 Days |  |  | RICARDO SINAGA | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Rejected | Done | 400000 | 2036-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_5327_SUM-SU-MDN-0299 | Need Revise |  | Bayu | need cek ZTE status alarm reject L2, Perf_Alert_WPL_IPPD_PL P2 P3 UAS alarm of radio Transmission unit link break PLA member port abnormal alarm Modem part unlock | MW
| 185 | 2026-01-17 | S1ID2025042515WBF1-41 | ZMDN_5327_SUM-SU-MDN-0299 | Danau Singkarak GMT_3G MC PABRIK TINUN PETISAH | 2026-01-22 | 4 Days | 2026-01-24 | 3 Days |  |  | RICARDO SINAGA | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2036-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_5327_SUM-SU-MDN-0299 | N/A
| 186 |  | S1ID2025042515WBF1-30 | NMDN_0097_SUM-SU-LBP-0337 | IBS Gang Segitiga_Marendal II Medan | 2026-01-14 | 4 Days | 2026-01-17 | 4 Days |  |  | RUDI GUNAWAN | Reroute | Reroute 2+0 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0097_SUM-SU-LBP-0337 | Closed_Cek TERM 2
| 187 |  | S1ID2025042515WBF1-30 | NMDN_0097_SUM-SU-LBP-0337 | IBS Gang Segitiga_Marendal II Medan | 2026-01-14 | 4 Days | 2026-01-17 | 4 Days |  |  | RUDI GUNAWAN | Reroute | Reroute 2+0 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2026-02-24 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0097_SUM-SU-LBP-0337 | N/A
| 188 | 2026-01-21 | S1ID2025042515WBF1-43 | ZMDN_4715_SUM-SU-LBP-0302 | MEDAN JOHOR 1_DELITUA KAMPUNG | 2026-01-18 | 4 Days | Done |  |  |  | RUDI GUNAWAN/RICARDO SINAGA-ATP | Reroute | Reroute 2+0 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Rejected | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4715_SUM-SU-LBP-0302 | Need Revise |  | Bayu | need cek ZTE status alarm_Approver reject, The link between the server and the NE is broken | MW
| 189 | 2026-01-21 | S1ID2025042515WBF1-43 | ZMDN_4715_SUM-SU-LBP-0302 | MEDAN JOHOR 1_DELITUA KAMPUNG | 2026-01-18 | 4 Days |  |  |  |  | RUDI GUNAWAN/RICARDO SINAGA-ATP | Reroute | Reroute 2+0 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4715_SUM-SU-LBP-0302 | N/A
| 190 | 2026-01-06 | S1ID2025042515WBF1-31 | SUM-SU-PMS-2106_SUM-SU-PMS-0959 | TUMORANG_Beringin Siantar | 2026-01-13 | 2 Days | 2026-01-13 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | SUM-SU-PMS-2106_SUM-SU-PMS-0959 | L1 Approved
| 191 | 2026-01-06 | S1ID2025042515WBF1-31 | SUM-SU-PMS-2335_SUM-SU-PMS-0920 | PARAPAT_Site Parapat | 2026-01-13 | 2 Days | 2026-01-13 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 0.6><0.3 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | Done | 100000 | 2026-04-29 |  |  |  | 1000000 | 0 | 1000000 | 0 | In Progress |  |  |  |  | SUM-SU-PMS-2335_SUM-SU-PMS-0920 | Term 10% Approve
| 192 | 2026-01-18 | S1ID2025042515WBF1-37 | SUM-SU-GNT-0071_SUM-SU-SBH-1068 | Mananti Tapanuli Selatan_BINANGA TAPSEL | 2026-01-22 | 2 Days | 2026-01-23 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle MW 1.8><1.2 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-04-13 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-GNT-0071_SUM-SU-SBH-1068 | Closed_Cek TERM 2
| 193 | 2026-01-20 | S1ID2025042515WBF1-44 | ZMDN_4999_SUM-SU-SRH-1943 | BOGAK KECIL_PANTAI LABUDusun III(SuperHUB102)(I)(G) | 2026-01-30 | 2 Days | 2026-01-31 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4999_SUM-SU-SRH-1943 | Closed_Cek TERM 1
| 194 | 2026-01-20 | S1ID2025042515WBF1-37 | ZMDN_4654_SUM-SU-LBP-0445 | Pantai Labu_Dusun Jogja | 2026-02-06 | 2 Days | 2026-02-06 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-04-13 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_4654_SUM-SU-LBP-0445 | Closed_Cek TERM 2
| 195 | 2026-01-20 | S1ID2025042515WBF1-38 | ZMDN_5414_SUM-SU-LBP-0228 | Karang Luas_Tandem Binjai 3 | 2026-02-03 | 2 Days | 2026-02-03 | 1 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_5414_SUM-SU-LBP-0228 | Closed_Cek TERM 2
| 196 | 2026-01-20 | S1ID2025042515WBF1-38 | ZMDN_4697_SUM-SU-LBP-0437 | Lubuk Pakam Jalan Lestari_ JL PURWO | 2026-02-04 | 2 Days | 2026-02-05 | 2 Days |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2036-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_4697_SUM-SU-LBP-0437 | Closed_Cek TERM 2
| 197 | 2026-02-20 | S1ID2025042515WBF1-38 | NMDN_0402_SUM-SU-LBP-0505 | Sukadono_Tanjung Gusta | 2026-02-02 | 2 Days | Done |  | Permit NE late released |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2036-02-03 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | NMDN_0402_SUM-SU-LBP-0505 | Closed_Cek TERM 3
| 198 | 2026-01-27 | S1ID2025042515WBF1-40 | SUM-SU-SBG-2227_SUM-SU-SBG-1185 | MAS_NAULI_Ruku-Ruku | 2026-02-07 | 4 Days | Done |  |  |  | RICARDO SINAGA | Swap Upgrade | Swap Upgrade 2+0 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | In review ZTE | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-SBG-2227_SUM-SU-SBG-1185 | In review ZTE | 09/05 Doc resubmit | Khairul | Waiting LBC revision _Khairul | MW
| 199 | 2026-01-27 | S1ID2025042515WBF1-40 | SUM-SU-SBG-2227_SUM-SU-SBG-1185 | MAS_NAULI_Ruku-Ruku | 2026-02-07 | 4 Days |  |  |  |  | RICARDO SINAGA | Swap Upgrade | Swap Upgrade 2+0 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-SBG-2227_SUM-SU-SBG-1185 | N/A
| 200 | 2026-01-27 | S1ID2025042515WBF1-40 | SUM-SU-SBH-0081_SUM-SU-SBH-1220 | Batang Bulu Tanggal Tapanuli Selatan_JLN_KIHAJAR_DEWANTARA | 2026-02-03 | 4 Days | 2026-02-06 | 4 Days |  |  | RICARDO SINAGA | Swap Upgrade | Swap Upgrade 2+0 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-SBH-0081_SUM-SU-SBH-1220 | Not Yet Submit |  | Khairul | Need Cek Khairul | MW
| 201 | 2026-01-27 | S1ID2025042515WBF1-40 | SUM-SU-SBH-0081_SUM-SU-SBH-1220 | Batang Bulu Tanggal Tapanuli Selatan_JLN_KIHAJAR_DEWANTARA | 2026-02-03 | 4 Days | 2026-02-06 | 4 Days |  |  | RICARDO SINAGA | Swap Upgrade | Swap Upgrade 2+0 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-SBH-0081_SUM-SU-SBH-1220 | N/A
| 202 | 2026-01-26 | S1ID2025042515WBF1-41 | SUM-SU-SBG-1188_SUM-SU-SBG-1190 | Barus_BUKIT_PATUPANGAN | 2026-02-07 | 4 Days | Done |  |  |  | RICARDO SINAGA | Reroute | Reroute 2+0 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Rejected | Done | 400000 | 2036-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-SBG-1188_SUM-SU-SBG-1190 | Need On Site |  |  | Need repointing RSL -33,7dbm_Khairul | MW
| 203 | 2026-01-26 | S1ID2025042515WBF1-41 | SUM-SU-SBG-1188_SUM-SU-SBG-1190 | Barus_BUKIT_PATUPANGAN | 2026-02-07 | 4 Days |  |  |  |  | RICARDO SINAGA | Reroute | Reroute 2+0 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2036-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-SBG-1188_SUM-SU-SBG-1190 | N/A
| 204 | 2026-01-26 | S1ID2025042515WBF1-36 | SUM-SU-PYB-1076_SUM-SU-PYB-1079 | Pati kubang_Pulo Padang | 2026-02-07 | 4 Days | Done |  |  |  | RUDI GUNAWAN | Reroute | Reroute 2+0 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | In review ZTE | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-PYB-1076_SUM-SU-PYB-1079 | In review ZTE | 09/05 Doc resubmit | Khairul | Need Revise_Khairul | MW
| 205 | 2026-01-26 | S1ID2025042515WBF1-36 | SUM-SU-PYB-1076_SUM-SU-PYB-1079 | Pati kubang_Pulo Padang | 2026-02-07 | 4 Days |  |  |  |  | RUDI GUNAWAN | Reroute | Reroute 2+0 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-PYB-1076_SUM-SU-PYB-1079 | N/A
| 206 | 2025-12-10 | S1ID2025042515WBF1-31 | SUM-SU-LMP-0993_SUM-SU-LMP-0457 | Bandar Tinggi_Laut Tador |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep | DSM ANT MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-10 | Done | 500000 | 2026-04-13 | Done | 100000 | 2026-04-29 |  |  |  | 1000000 | 0 | 1000000 | 0 | In Progress |  |  |  |  | SUM-SU-LMP-0993_SUM-SU-LMP-0457 | Term 10% Approve
| 207 | 2026-01-27 | S1ID2025042515WBF1-40 | SUM-SU-PSP-1046_SUM-SU-PSP-1544 | Arse_BARINGIN TAPANULI SELATAN | 2026-02-06 | 4 Days | Done |  |  |  | RUDI GUNAWAN | Reroute | Reroute 2+0 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | L1 Approved | Done | 400000 | 2026-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-PSP-1046_SUM-SU-PSP-1544 | L1 Approved |  |  | Done Submit 06 May Khairul | MW
| 208 | 2026-01-27 | S1ID2025042515WBF1-40 | SUM-SU-PSP-1046_SUM-SU-PSP-1544 | Arse_BARINGIN TAPANULI SELATAN | 2026-02-06 | 4 Days |  |  |  |  | RUDI GUNAWAN | Reroute | Reroute 2+0 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2026-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-PSP-1046_SUM-SU-PSP-1544 | N/A
| 209 | 2026-01-26 | S1ID2025042515WBF1-40 | SUM-AC-JTH-0623_SUM-AC-JTH-0606 | PASI JANENG_LAMPUYANG ACEH BESAR | 2026-02-06 | 6 Days | Done |  |  |  | ANGGA WIJAYA | Swap Upgrade | Swap Upgrade 2+0 SD | Nanggroe Aceh | North Sumatra | 350000275824 | I&C-Seperate MW+0.3-0.6m Antenna (SD)4 | 1000000 |  | Done | Outbound Done | L1 Approved | Done | 400000 | 2026-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-JTH-0623_SUM-AC-JTH-0606 | L1 Approved |  |  |  | MW
| 210 | 2026-01-26 | S1ID2025042515WBF1-40 | SUM-AC-JTH-0623_SUM-AC-JTH-0606 | PASI JANENG_LAMPUYANG ACEH BESAR | 2026-02-06 | 6 Days |  |  |  |  | ANGGA WIJAYA | Swap Upgrade | Swap Upgrade 2+0 SD | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | Done | 400000 | 2026-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-AC-JTH-0623_SUM-AC-JTH-0606 | N/A
| 211 | 2026-01-20 | S1ID2025042515WBF1-51 | SUM-AC-JTH-0623_SUM-AC-JTH-0606 | PASI JANENG_LAMPUYANG ACEH BESAR | 2026-02-06 | 6 Days | Done |  |  |  | ANGGA WIJAYA | Dismantle MW Keep | DSM SD 1.2(2PCS), 0.6(2 PCS) | Nanggroe Aceh | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-JTH-0623_SUM-AC-JTH-0606 | Closed_Cek TERM 1
| 212 | 2026-02-01 | S1ID2025042515WBF1-38 | NMDN_0828_SUM-SU-LMP-0462 | Lintas Sumatera Indrapura Air Putih_Kampung Aras |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-03 | Done | 500000 | 2026-04-13 | [6 empty] | 900000 | 0 | 900000 | 100000 | In Progress |  |  |  |  | NMDN_0828_SUM-SU-LMP-0462 | Closed_NEED OPEN TASK PAC
| 213 | 2026-02-01 | S1ID2025042515WBF1-38 | NMDN_0746_SUM-SU-LBP-0367 | Dusun X Amal Bakti_Tembung 10 I |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep | DISMANTLE MW ANT 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-02-03 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0746_SUM-SU-LBP-0367 | Closed_Cek TERM 2
| 214 | 2026-02-05 | S1ID2025042515WBF1-51 | ZMDN_4715_SUM-SU-LBP-0302 | MEDAN JOHOR 1_KEDAI DURIAN (KIMSARI) |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep | DISMANTLE MW ANT 0.3 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4715_SUM-SU-LBP-0302 | Closed_Cek TERM 1
| 215 | 2026-02-05 | S1ID2025042515WBF1-37 | ZMDN_5327_SUM-SU-MDN-0299 | MC JOHOR6_Kedai Durian I |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep | DISMANTLE MW ANT 0.3 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-04-13 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_5327_SUM-SU-MDN-0299 | Closed_Cek TERM 2
| 216 | 2026-02-05 | S1ID2025042515WBF1-37 | ZMDN_4907_SUM-SU-MDN-0824 | Sutrisno - Medan Area_Wahidin |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep | DISMANTLE MW ANT 0.3 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | Done | 400000 | 2026-04-13 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_4907_SUM-SU-MDN-0824 | L1 Approved |  |  | 0605 Approver reject, Error sign 0705 Doc Submit | Dismantle
| 217 | 2026-02-10 | S1ID2025042515WBF1-37 | NMDN_0156_SUM-SU-PMS-0941 | Bane bali(SuperHUB33)(I)(G)_Naga Huta(SuperHUB47)(I)(G) |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep | DISMANTLE MW ANT 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-04-13 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | NMDN_0156_SUM-SU-PMS-0941 | Closed_Cek TERM 2
| 218 | 2026-02-10 | S1ID2025042515WBF1-37 | SUM-SU-SBH-0081_SUM-SU-SBH-1220 | Batang Bulu Tanggal Tapanuli Selatan_JLN_KIHAJAR_DEWANTARA | 2026-02-19 | 2 Days | 2026-02-20 | 2 Days |  |  | RUDI GUNAWAN | Dismantle MW Keep | Dismantle Ant 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-SBH-0081_SUM-SU-SBH-1220 | L1 Approved
| 219 | 2026-02-10 | S1ID2025042515WBF1-47 | SUM-SU-PRR-2221_SUM-SU-PRR-1002 | PANGURURAN SAMOSIR_PANGURURAN |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep | Dismantle Ant 0.9 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | Done | 400000 | 2026-04-13 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | SUM-SU-PRR-2221_SUM-SU-PRR-1002 | Closed_Cek TERM 2
| 220 | 2026-02-10 | S1ID2025042515WBF1-44 | SUM-AC-BIR-0593_SUM-AC-BIR-0271 | Peusangan BIREUEN Bawah_Jeunib |  |  | Done |  |  |  | ANGGA WIJAYA | Dismantle MW Keep | Dismantle Ant 1.8 | Nanggroe Aceh | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-BIR-0593_SUM-AC-BIR-0271 | Closed_Cek TERM 1
| 221 | 2026-02-10 | S1ID2025042515WBF1-44 | SUM-AC-BIR-0011_SUM-AC-BIR-0352 | Juli_4217_Bireuen | 2026-03-12 | 2 Days | 2026-03-13 | 2 Days |  |  | ANGGA WIJAYA | Dismantle MW Keep | DSM Ant MW 1.2 | Nanggroe Aceh | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-BIR-0011_SUM-AC-BIR-0352 | Closed_Cek TERM 1
| 222 | 2026-02-20 | S1ID2025042515WBF1-44 | NMDN_0517_SUM-SU-PSP-1217 | SF_POP Hapesong Lama_SF_SU-821140 |  |  | Done |  |  |  | ANGGA WIJAYA | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Rejected | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0517_SUM-SU-PSP-1217 | Rejected |  |  | Approver reject, Site Id berbeda
| 223 | 2026-02-20 | S1ID2025042515WBF1-44 | SUM-SU-PYB-1076_SUM-SU-PYB-1079 |  |  |  | Done |  |  |  | ANGGA WIJAYA | Dismantle MW Keep | DSM Ant MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-PYB-1076_SUM-SU-PYB-1079 | Not Yet Submit
| 224 | 2026-02-20 | S1ID2025042515WBF1-44 | SUM-SU-KIS-2224_SUM-SU-KIS-0181 | SIMPANG_EMPAT_JAMPALAN_Simpang Kawat Kisaran |  |  | Done |  |  |  | ANGGA WIJAYA | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-KIS-2224_SUM-SU-KIS-0181 | L1 Approved
| 225 | 2026-02-10 | S1ID2025042515WBF1-47 | ZMDN_5341_SUM-SU-PMS-0946 |  |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Not Yet Submit | Done | 400000 | 2026-04-13 | [9 empty] | 400000 | 0 | 400000 | 600000 | In Progress |  |  |  |  | ZMDN_5341_SUM-SU-PMS-0946 | Not Yet Submit
| 226 | 2026-02-20 | S1ID2025042515WBF1-46 | SUM-AC-JTH-0080_SUM-AC-JTH-0553 | JANTHO_Lampisang Teungoh ACEH BESAR |  |  | Done |  |  |  | VALDINO RAWUNG | Reroute | Reroute 2+0 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Rejected | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-JTH-0080_SUM-AC-JTH-0553 | Need On Site |  |  | Need repointing_Bayu | MW
| 227 | 2026-02-20 | S1ID2025042515WBF1-46 | SUM-AC-JTH-0080_SUM-AC-JTH-0553 | JANTHO_Lampisang Teungoh ACEH BESAR | [6 empty] | VALDINO RAWUNG | Reroute | Reroute 2+0 | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-JTH-0080_SUM-AC-JTH-0553 | N/A
| 228 | 2026-03-01 | S1ID2025042515WBF1-44 | SUM-SU-SBG-1188_SUM-SU-SBG-1190 | Barus_BUKIT_Andam Dewi |  |  | Done |  |  |  | RICARDO SINAGA | Dismantle MW Keep | DSM Ant MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-SBG-1188_SUM-SU-SBG-1190 | Closed_Cek TERM 1
| 229 | 2026-01-28 | S1ID2025042515WBF1-44 | SUM-SU-SBG-2227_SUM-SU-SBG-1185 | MAS_NAULI_Ruku-Ruku |  |  | Done |  |  |  | RICARDO SINAGA | Dismantle MW Keep | DSM Ant MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-SBG-2227_SUM-SU-SBG-1185 | Closed_Cek TERM 1
| 230 | 2026-02-20 | S1ID2025042515WBF1-48 | SUM-AC-SAB-0455_SUM-AC-SAB-0172 | 3G JURONG_Cot Batte Tamon |  |  | Done |  |  |  | FERNANDO | Swap Upgrade | Swap Upgrade 2+0 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-SAB-0455_SUM-AC-SAB-0172 | Need ISR |  |  | Need ISR | MW
| 231 | 2026-02-20 | S1ID2025042515WBF1-48 | SUM-AC-SAB-0455_SUM-AC-SAB-0172 | 3G JURONG_Cot Batte Tamon | [6 empty] | FERNANDO | Swap Upgrade | Swap Upgrade 2+0 | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-SAB-0455_SUM-AC-SAB-0172 | N/A
| 232 | 2026-02-18 | S1ID2025042515WBF1-44 | NMDN_0097_SUM-SU-LBP-0337 | IBS Gang Segitiga_Sempurna | 2026-02-20 | 2 Days | 2026-02-23 | 3 Days | issue access |  | VALDINO RAWUNG | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0097_SUM-SU-LBP-0337 | Closed_Cek TERM 1
| 233 | 2026-02-20 | S1ID2025042515WBF1-48 | SUM-AC-JTH-0602_SUM-AC-JTH-0080 | JANTHO BARU_JANTHO | 2026-03-04 | 4 Days | Done |  |  |  | VALDINO RAWUNG | Reroute | Reroute 2+0_ANT MW 0.6m | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-JTH-0602_SUM-AC-JTH-0080 | Closed_Cek TERM 1
| 234 | 2026-02-20 | S1ID2025042515WBF1-48 | SUM-AC-JTH-0602_SUM-AC-JTH-0080 | JANTHO BARU_JANTHO | 2026-03-04 | 4 Days |  |  |  |  | VALDINO RAWUNG | Reroute | Reroute 2+0_ANT MW 0.6m | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-JTH-0602_SUM-AC-JTH-0080 | N/A
| 235 | 2026-03-05 | S1ID2025042515WBF1-50 | SUM-AC-SAB-0172_SUM-AC-SAB-0473 | Cot Batte Tamon_ANOI HITAM SABANG |  |  | Done |  |  |  | FERNANDO | New Link | New Link 2+0 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-SAB-0172_SUM-AC-SAB-0473 | L1 Approved |  |  |  | MW
| 236 | 2026-03-15 | S1ID2025042515WBF1-52 | SUM-SU-AKK-0016_SUM-SU-AKK-1152 | BILAH_HULU_LABUHAN_Perbaungan Bilah Hulu |  |  | Done |  |  |  | ANGGA WIJAYA | New Link | New Link 2+0 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Closed with PL | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-AKK-0016_SUM-SU-AKK-1152 | Need On Site |  |  |  | CPL
| 237 | 2026-03-15 | S1ID2025042515WBF1-49 | SUM-SU-AKK-0016 | BILAH_HULU_LABUHAN |  |  | Done |  |  |  | FERNANDO | New Site | RAN ONLY | North Sumatra | North Sumatra |  |  | 1350000 |  | Done | Outbound Done | L2 Approved | [12 empty] | 0 | 0 | 0 | 1350000 | In Progress | Blocking access [issue imbas petir TP belum membayar kompensasi sehingga tidak di izinkan oleh masyarakat] ; Doc dikerjakan Gadis |  |  |  | SUM-SU-AKK-0016 | L2 Approved
[17 empty] | 350001003161 | XLSmart_RRU installation/expansion(RRU Qty(4-6)) |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003171 | XLSmart_RF Antenna installation(Antenna Qty(1-3)) |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003180 | XLSmart_Wireless site commissioning (on Mobile phone) |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003181 | XLSmart_Wireless As built document and ATP |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003186 | XLSmart_DBS site board expansion |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003191 | XLSmart_Filter installation Qty(1-3) |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003197 | XLSmart_GPS installation |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003252 | XLSmart_DC Power distribution system installation&commissioning&ATP(DC distribution cabinet) |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003253 | XLSmart_Battery _48V Lithium Battery Bank(1～2)_Installation |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
| 238 | 2026-03-31 | Waiting Release | SUM-SU-AKK-0058 | SEI TAWAR |  |  | Done |  |  |  | ANGGA WIJAYA | New Site | RAN ONLY | North Sumatra | North Sumatra |  |  | 1350000 |  | Done | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1350000 | In Progress | Waiting PLN ; Install done (minus NY perkabelan NY Install) ; NY Integrasi : NY Collect data ; NY Start Document |  |  |  | SUM-SU-AKK-0058 | Not Yet Submit |  |  | Waiting PLN ; Install done (minus NY perkabelan NY Install) ; NY Integrasi : NY Collect data ; NY Start Document
[8 empty] | Done | [8 empty] | 350001003161 | XLSmart_RRU installation/expansion(RRU Qty(4-6)) |  | 150000 |  |  | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003171 | XLSmart_RF Antenna installation(Antenna Qty(1-3)) |  | 150000 |  |  | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003180 | XLSmart_Wireless site commissioning (on Mobile phone) |  | 150000 |  |  | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003181 | XLSmart_Wireless As built document and ATP |  | 150000 |  |  | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003186 | XLSmart_DBS site board expansion |  | 150000 |  |  | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003191 | XLSmart_Filter installation Qty(1-3) |  | 150000 |  |  | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003197 | XLSmart_GPS installation |  | 150000 |  |  | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003252 | XLSmart_DC Power distribution system installation&commissioning&ATP(DC distribution cabinet) |  | 150000 |  |  | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003253 | XLSmart_Battery _48V Lithium Battery Bank(1～2)_Installation |  | 150000 |  |  | NO NEED | [12 empty] | 0 | 0 | 0 | 0
| 239 | 2026-03-31 | S1ID2025042515WBF1-56 | SUM-SU-AKK-0058_SUM-SU-AKK-1681 | SEI TAWAR_/Tanjung Sarang Elang LABUHAN BATU | 2026-04-16 |  | Done |  | New site waiting PLN, install done |  | ANGGA WIJAYA | New Link | New Link 1+0 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-AKK-0058_SUM-SU-AKK-1681 | Hold |  |  | install mw+ran done waiting PLN
| 240 | 2026-03-01 | S1ID2025042515WBF1-58 | SUM-AC-JTH-0602_SUM-AC-JTH-0392 | JANTHO BARU_JANTHO |  |  | Done |  |  |  | VALDINO RAWUNG | Dismantle MW Keep |  | Nanggroe Aceh | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-JTH-0602_SUM-AC-JTH-0080 | L1 Approved |  |  | Doc submit_Bayu | Dismantle
| 241 | 2026-03-01 | Waiting Release | SUM-AC-JTH-0080_SUM-AC-JTH-0077 | JANTHO_Lampisang Teungoh ACEH BESAR |  |  | Done |  |  |  | VALDINO RAWUNG | Dismantle MW Keep |  | Nanggroe Aceh | North Sumatra |  |  |  |  | Not yet start | Not Yet Start | Not Yet Start | [12 empty] | 0 | 0 | 0 | 0 | In Progress | NY dismantle waiting migration by ZTE |  |  |  | SUM-AC-JTH-0080_SUM-AC-JTH-0077 | Not Yet Start_Need PO |  |  | NY dismantle waiting migration by ZTE
| 242 | 2026-03-01 | Waiting Release | SUM-SU-DLS-8021_SUM-SU-DLS-0062 | HUTAGURGUR_DolokMargu |  |  | Done |  |  |  | RUDI GUNAWAN | Dismantle MW Keep | DSM Ant MW 1.8><1.2 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-DLS-8021_SUM-SU-DLS-0062 | Closed_Need PO
| 243 | 2026-03-14 | S1ID2025042515WBF1-63 | SUM-SU-TRT-2015_SUM-SU-TRT-1423 | DOLOKSARIBU_SIPULTAK DOLOK |  |  | Done |  |  |  | RUDI GUNAWAN | Dismantle MW Keep | DSM Ant MW 0.6 | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-TRT-2015_SUM-SU-TRT-1423 | L1 Approved_Need PO
| 244 | 2026-03-14 | S1ID2025042515WBF1-58 | NMDN_0802_SUM-SU-MDN-0540 | AMAL LUHUR_Asrama Medan |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0802_SUM-SU-MDN-0540 | L1 Approved |  |  | 0605 Approver reject L2, Site Id berbeda 0705 Doc Submit | Dismantle
| 245 | 2026-03-14 | S1ID2025042515WBF1-58 | NMDN_0034_SUM-SU-LBP-0411 | IBS Gang turi_Desa Skip |  |  | Done |  |  |  | RICARDO SINAGA | Dismantle MW Keep | DSM Ant MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0034_SUM-SU-LBP-0411 | Closed
| 246 | 2026-03-20 | S1ID2025042515WBF1-58 | SUM-SU-PSP-1046_SUM-SU-PSP-1544 | Arse_Huraba |  |  | Done |  |  |  | RUDI GUNAWAN | Dismantle MW Keep | DSM Ant MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-PSP-1046_SUM-SU-PSP-1544 | L1 Approved_Need PO
| 247 | 2026-03-20 | S1ID2025042515WBF1-58 | ZMDN_4118_ZMDN_4168 | Medan Estate_Bandar Selamat |  |  | Done |  |  |  | WAHYU WIBISONO | Dismantle MW Keep | DSM Ant MW 1.2><0.6 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4118_SUM-SU-LBP-0338 | L1 Approved_Need PO
| 248 | 2026-03-20 | S1ID2025042515WBF1-58 | ZMDN_4085_NMDN_0133 | R.Sidikalang-Kotarame_Perdagangan Sidikalang |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep | DSM Ant MW 1.2 | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4085_NMDN_0133 | Not Yet Submit_Need PO
| 249 | 2026-03-20 | Waiting Release | ZMDN_4088_ZMDN_4112 | Mistar-S.Putih Barat_Jamin Ginting |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4088_ZMDN_4112 | Not Yet Submit_Need PO
| 250 | 2026-03-20 | S1ID2025042515WBF1-61 | SUM-SU-MDN-2635_SUM-SU-MDN-0697 | Grand Palladium Mall_Hotel Grand Aston City Hall Medan (Leasi |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-MDN-2635_SUM-SU-MDN-0697 | Not Yet Submit_Need PO
| 251 | 2026-03-20 | S1ID2025042515WBF1-58 | NMDN_0703_SUM-SU-MDN-0525 | Telkom Padang Bulan_Kenanga Sari |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0703_SUM-SU-MDN-0525 | L1 Approved |  |  | 0605 Approver reject L2, Site Id berbeda 0705 Doc Submit | Dismantle
| 252 | 2026-03-20 | Waiting Release | SUM-SU-PMS-1889_SUM-SU-PMS-0981 | Simpang Bah Jambi_Serapuh | [6 empty] | RUDI GUNAWAN | Dismantle MW Keep |  | North Sumatra | North Sumatra |  |  |  |  | Not yet start | Not Yet Start | Not Yet Start | [12 empty] | 0 | 0 | 0 | 0 | In Progress | NY dismantle blocking access Imbas petir |  |  |  | SUM-SU-PMS-1889_SUM-SU-PMS-0981 | Not Yet Start_Need PO |  |  | NY dismantle blocking access Imbas petir
| 253 | 2026-03-20 | S1ID2025042515WBF1-63 | ZMDN_4045_SUM-SU-SRH-2234 | IBS SUNGAI BULUH_Desa Skip |  |  | Done |  |  |  | RICARDO SINAGA | Dismantle MW Keep | DSM Ant MW 1.8 | North Sumatra | North Sumatra | 350000190027 | Dismantling&Simple Packing: MW+1.3-2.0m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_4045_SUM-SU-SRH-2234 | L1 Approved |  |  | Doc submit_Bayu | Dismantle
| 254 | 2026-03-31 | RETURN TO ZTE | SUM-SU-AKK-0010_SUM-SU-AKK-1109 | KUALUH_HULU_Londut Selatan | [7 empty] | New Link | New Link 2+0 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 |  |  | Return to ZTE | Return to ZTE | Return to ZTE | [12 empty] | 0 | 0 | 0 | 0 | In Progress | Tower NY RFI ; Assignment di kembalikan ke ZTE ; Claim PO Transportasi WH ZTE to Site |  |  |  | SUM-SU-AKK-0010_SUM-SU-AKK-1109 | Return to ZTE |  |  | Tower NY RFI ; Assignment di kembalikan ke ZTE ; Claim PO Transportasi WH ZTE to Site
| 255 | 2026-03-31 | S1ID2025042515WBF1-59 | SUM-SU-TJB-0001 |  |  |  | Done |  |  |  | RINALDI | New Site | RAN ONLY | North Sumatra | North Sumatra |  |  | 1350000 |  | Done | Outbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1350000 | In Progress | Untuk Documen sementara di handle Bayu & Pak Wahyu |  |  |  | SUM-SU-TJB-0001 | L1 Approved_Need PO
[17 empty] | 350001003161 | XLSmart_RRU installation/expansion(RRU Qty(4-6)) |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003171 | XLSmart_RF Antenna installation(Antenna Qty(1-3)) |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003180 | XLSmart_Wireless site commissioning (on Mobile phone) |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003181 | XLSmart_Wireless As built document and ATP |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003186 | XLSmart_DBS site board expansion |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003191 | XLSmart_Filter installation Qty(1-3) |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003197 | XLSmart_GPS installation |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003252 | XLSmart_DC Power distribution system installation&commissioning&ATP(DC distribution cabinet) |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003253 | XLSmart_Battery _48V Lithium Battery Bank(1～2)_Installation |  | 150000 | [15 empty] | 0 | 0 | 0 | 0
| 256 | 2026-03-31 | RETURN TO ZTE | SUM-SU-AKK-0010 | KUALUH_HULU | [7 empty] | New Site | RAN ONLY | North Sumatra | North Sumatra |  |  |  |  | Return to ZTE | Return to ZTE | Return to ZTE | [12 empty] | 0 | 0 | 0 | 0 | In Progress | Tower NY RFI ; Assignment di kembalikan ke ZTE ; Claim PO Transportasi Site to WH ZTE |  |  |  | SUM-SU-AKK-0010 | Return to ZTE |  |  | Tower NY RFI ; Assignment di kembalikan ke ZTE ; Claim PO Transportasi WH ZTE to Site
[17 empty] | 350001003161 | XLSmart_RRU installation/expansion(RRU Qty(4-6)) |  | 5186148 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003171 | XLSmart_RF Antenna installation(Antenna Qty(1-3)) |  | 2671944 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003180 | XLSmart_Wireless site commissioning (on Mobile phone) |  | 2668116 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003181 | XLSmart_Wireless As built document and ATP |  | 1662672 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003186 | XLSmart_DBS site board expansion |  | 377916 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003191 | XLSmart_Filter installation Qty(1-3) |  | 585816 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003197 | XLSmart_GPS installation |  | 822360 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003252 | XLSmart_DC Power distribution system installation&commissioning&ATP(DC distribution cabinet) |  | 1762992 | [15 empty] | 0 | 0 | 0 | 0
[17 empty] | 350001003253 | XLSmart_Battery _48V Lithium Battery Bank(1～2)_Installation |  | 1735140 | [15 empty] | 0 | 0 | 0 | 0
| 257 | 2026-03-31 | S1ID2025042515WBF1-54 | ENT-SU-AKK-0006_SUM-SU-AKK-2001 |  |  |  | Done |  |  |  | ANGGA WIJAYA | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ENT-SU-AKK-0006_SUM-SU-AKK-2001 | Not Yet Submit |  | Bayu | Need Cek Bayu | MW
| 258 | 2026-03-31 | S1ID2025042515WBF1-54 | ENT-SU-AKK-0006_SUM-SU-AKK-2001 |  |  |  | Done |  |  |  | ANGGA WIJAYA | Reroute | Reroute 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ENT-SU-AKK-0006_SUM-SU-AKK-2001 | N/A
| 259 | 2026-04-02 | S1ID2025042515WBF1-54 | SUM-SU-PMS-0906_SUM-SU-PMS-0912 |  |  |  | Done |  |  |  | RICARDO SINAGA | Reroute | Reroute 2+0_Ant MW 1.2 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Need Revise | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-PMS-0906_SUM-SU-PMS-0912 | Need Revise | 09/05 Doc Submit | Bayu | Doc Resubmit_Bayu | MW
| 260 | 2026-04-02 | S1ID2025042515WBF1-54 | SUM-SU-PMS-0906_SUM-SU-PMS-0912 |  |  |  | Done |  |  |  | RICARDO SINAGA | Reroute | Reroute 2+0_Ant MW 1.2 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-PMS-0906_SUM-SU-PMS-0912 | N/A
| 261 | 2026-03-20 | S1ID2025042515WBF1-58 | SUM-AC-KTN-0382_SUM-AC-KTN-0103 |  |  |  | Done |  |  |  | RUDI GUNAWAN | Dismantle MW Keep | DSM ANT MW 0.6 | Nanggroe Aceh | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-KTN-0382_SUM-AC-KTN-0103 | L1 Approved |  |  | DocSubmit_Bayu | Dismantle
| 262 | 2026-04-06 | S1ID2025042515WBF1-54 | SUM-SU-STB-2203_SUM-SU-STB-1389 |  |  |  | Done |  |  |  | FERNANDO | Swap Upgrade | Swap Upgrade 2+0_Ant MW 1.2 | North Sumatra | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Done | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-STB-2203_SUM-SU-STB-1389 | Not Yet Submit |  | Nungki | Revisi LBC krn pointing 36dbm, buget LBC 32dbm_Team on site (Rinaldi) 0705 Team Rinaldi / Dedek Anggara on site | MW
| 263 | 2026-04-06 | S1ID2025042515WBF1-54 | SUM-SU-STB-2203_SUM-SU-STB-1389 |  |  |  | Done |  |  |  | FERNANDO | Swap Upgrade | Swap Upgrade 2+0_Ant MW 1.2 | North Sumatra | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-STB-2203_SUM-SU-STB-1389 | N/A
| 264 | 2026-04-07 | S1ID2025042515WBF1-54 | SUM-SU-AKK-0061_SUM-SU-AKK-0042 | Piandang Batu_SELATBESAR |  |  | Done |  |  |  | RUDI GUNAWAN | New Link | New Link 1+0_Ant MW 0.6 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-AKK-0061_SUM-SU-AKK-0042 | Not Yet Submit |  | Bayu | Need Cek Bayu | MW
| 265 | 2026-04-07 | S1ID2025042515WBF1-55 | SUM-SU-AKK-0061 | Piandang Batu |  |  | Done |  |  |  | RUDI GUNAWAN | New Site | RAN ONLY | North Sumatra | North Sumatra |  |  | 1350000 |  | Done | Outbound Done | Closed | [12 empty] | 0 | 0 | 0 | 1350000 | In Progress | Document Done by Angga |  |  |  | SUM-SU-AKK-0061 | Closed_Cek Termin 1
[8 empty] | Done | [8 empty] | 350001003161 | XLSmart_RRU installation/expansion(RRU Qty(4-6)) |  | 150000 |  | Outbound Done | [13 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003171 | XLSmart_RF Antenna installation(Antenna Qty(1-3)) |  | 150000 |  | N/A | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003180 | XLSmart_Wireless site commissioning (on Mobile phone) |  | 150000 |  | N/A | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003181 | XLSmart_Wireless As built document and ATP |  | 150000 |  | N/A | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003186 | XLSmart_DBS site board expansion |  | 150000 |  | N/A | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003191 | XLSmart_Filter installation Qty(1-3) |  | 150000 |  | N/A | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003197 | XLSmart_GPS installation |  | 150000 |  | N/A | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003252 | XLSmart_DC Power distribution system installation&commissioning&ATP(DC distribution cabinet) |  | 150000 |  | N/A | NO NEED | [12 empty] | 0 | 0 | 0 | 0
[8 empty] | Done | [8 empty] | 350001003253 | XLSmart_Battery _48V Lithium Battery Bank(1～2)_Installation |  | 150000 |  | N/A | NO NEED | [12 empty] | 0 | 0 | 0 | 0
| 266 | 2026-03-09 | S1ID2025042515WBF1-58 | NMDN_0803_ZMDN_4929 | PANDAU HULU 1 |  |  | Done |  |  | Dismantle 1/2 Hop Take over dari telkom infra | RINALDI | Dismantle MW Keep | Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | NMDN_0803_SUM-SU-MDN-0861 | L1 Approved |  |  | DocSubmit_Bayu | Dismantle
| 267 | 2026-04-19 | S1ID2025042515WBF1-63 | SUM-SU-PMS-0906_SUM-SU-PMS-0908 | Raya_Simalungun_Sibuntuan |  |  | Done |  |  |  | RINALDI | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-PMS-0906_SUM-SU-PMS-0912 | L1 Approved |  |  |  | Dismantle
| 268 | 2026-04-15 | S1ID2025042515WBF1-56 | SUM-AC-KRB-1311_SUM-AC-KRB-1315 | SUKA_MULIA_UPAH_UPAH |  |  | Done |  |  |  | VALDINO RAWUNG | Reroute | Reroute 2+0 | Nanggroe Aceh | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-KRB-1311_SUM-AC-KRB-1315 | L1 Approved |  |  | Done Submit 05 May_Bayu | MW
| 269 | 2026-04-15 | S1ID2025042515WBF1-56 | SUM-AC-KRB-1311_SUM-AC-KRB-1315 | SUKA_MULIA_UPAH_UPAH |  |  | Done |  |  |  | VALDINO RAWUNG | Reroute | Reroute 2+0 | Nanggroe Aceh | North Sumatra | 350000275879 | MW Cut-over | 1000000 |  | N/A | N/A | N/A | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-AC-KRB-1311_SUM-AC-KRB-1315 | N/A
| 270 | 2026-04-17 | Waiting Release | SUM-SU-MDN-0801_SUM-SU-MDN-0779 | [7 empty] | NOT YET ASSIGN TO TEAM | Dismantle MW Keep |  | North Sumatra | North Sumatra |  |  |  |  | Not yet start | Not Yet Start | Not Yet Start | [12 empty] | 0 | 0 | 0 | 0 | In Progress | NY dismantle hard comcase di request 5 mio belum di approve oleh ZTE |  |  |  | SUM-SU-MDN-0801_SUM-SU-MDN-0779 | Not Yet Start_Need PO |  |  | NY dismantle hard comcase di request 5 mio belum di approve oleh ZTE
| 271 | 2026-04-17 | S1ID2025042515WBF1-65 | SUM-SU-SRH-2086_SUM-SU-SRH-1263 | GUDANG GARAM_DOLOK MANAMPANG |  |  | Done |  |  |  | RICARDO SINAGA | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-SRH-2086_SUM-SU-SRH-1263 | L1 Approved |  |  | Doc submit_Bayu | Dismantle
| 272 | 2026-01-25 | Waiting Release | ZMDN_5341_SUM-SU-PMS-0946 | PEMATANGSIANTAR ex. MILLENIUM PONSEL_DWIKORA |  |  | Done |  |  |  | TEAM EXTERNAL | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ZMDN_5341_SUM-SU-PMS-0946 | Not Yet Start_Need PO
ok | 273 | 2026-04-15 | S1ID2025042515WBF1-63 | ENT-SU-AKK-0006_SUM-SU-AKK-1137 | BANK SINARMAS_Rantau Prapat Timur |  |  | Done |  |  |  | VALDINO RAWUNG | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ENT-SU-AKK-0006_SUM-SU-AKK-1137 | Not Yet Start_Need PO
| 274 | 2026-04-15 | S1ID2025042515WBF1-63 | SUM-SU-STB-2203_SUM-SU-STB-1389 | SECANGGANG_PERKOTAAN_PERKOTAAN BINJAI |  |  | Done |  |  |  | RICARDO SINAGA | Dismantle MW Keep |  | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | Inbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-STB-2203_SUM-SU-STB-1389 | Not Yet Submit_Need PO
| 275 | 2026-04-15 | S1ID2025042515WBF1-63 | SUM-AC-KRB-1311_SUM-AC-KRB-0094 | SUKA_MULIA_UPAH_Kuala Simpang Pertamina |  |  | Done |  |  |  | VALDINO RAWUNG | Dismantle MW Keep |  | Nanggroe Aceh | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Inbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 3608418 | In Progress |  |  |  |  | SUM-AC-KRB-1311_SUM-AC-KRB-1315 | L1 Approved |  |  | Waiting open task from ZTE | Dismantle
| 276 | 2026-04-21 | Waiting Release | SUM-SU-LBP-0217_SUM-SU-LBP-1469 | TELAGA SARI_ |  |  | Done |  |  |  | WAHYU WIBISONO | Survey | MW LOS survey | North Sumatra | North Sumatra | 350000190099 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Waiting Closed ZTE | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress | Task di FE LBP-1469 hilamg need on site |  |  |  | SUM-SU-LBP-0217_SUM-SU-LBP-0210 | Waiting Closed ZTE |  |  | Doc submit_Bayu | Survey
| 277 | 2026-04-21 | Waiting Release | SUM-AC-STR-0215_SUM-AC-STR-0214 | PONDOK BARU_SIMPANG TIGA |  |  | Done |  |  |  | VALDINO RAWUNG | Survey | MW LOS survey | Nanggroe Aceh | North Sumatra | 350000198247 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Waiting Closed ZTE | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress | Summary OK |  |  |  | SUM-AC-STR-0215_SUM-AC-STR-0214 | Waiting Closed ZTE |  |  | Summary OK | Survey
| 278 | 2026-04-21 | Waiting Release | SUM-AC-STR-0214_SUM-AC-TKN-0210 | SIMPANG TIGA_Simpang Tritit |  |  | Done |  |  |  | VALDINO RAWUNG | Survey | MW LOS survey | Nanggroe Aceh | North Sumatra | 350000198247 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Waiting Closed ZTE | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress | Summary OK |  |  |  | SUM-AC-STR-0214_SUM-AC-TKN-0210 | Waiting Closed ZTE |  |  | Summary OK | Survey
| 279 | 2026-04-21 | Waiting Release | SUM-SU-TRT-0061_SUM-SU-DLS-0056 | PARMONANGAN_ ONAN GANJANG | 2026-04-28 |  | OG FE |  | Reroute FE |  | BENI-RUDI | Survey | MW LOS survey | North Sumatra | North Sumatra | 350000190099 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Rejected | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress | Plan re route FE |  |  |  | SUM-SU-TRT-0061_SUM-SU-DLS-0007 | Team OTW |  | Rudi |  | Survey
| 280 | 2026-04-21 | Waiting Release | SUM-SU-SDK-2080_SUM-SU-SDK-1923 | SIDIKALANG3 | 2026-04-27 |  | 2026-04-30 |  | Block Access, Reroute FE |  | BENI | Survey | MW LOS survey | North Sumatra | North Sumatra | 350000190099 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Waiting Closed ZTE | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress | SUM-SU-SDK-1232 block access, survey reroute ke SUM-SU-SDK-1923 |  |  |  | SUM-SU-SDK-2080_SUM-SU-SDK-1923 | Waiting Closed ZTE |  |  | Summary OK | Survey
| 281 | 2026-04-21 | Waiting Release | SUM-SU-DLS-0056_SUM-SU-DLS-8021 | Onan Ganjang_Parmonangan | 2026-04-30 |  | OG FE |  | Reroute FE |  | BENI-RUDI | Survey | MW LOS survey | North Sumatra | North Sumatra | 350000190099 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Rejected | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress | Plan re route FE |  |  |  | SUM-SU-DLS-0056_SUM-SU-DLS-2397 | Team On Site | 10/05 Survey TSSR | Rudi |  | Survey
| 282 | 2026-04-22 | S1ID2025042515WBF1-64 | SUM-SU-TJB-0001_SUM-SU-TJB- 0187 | DATUK_BANDAR_TIMUR_Site Tanjung Balai |  |  | Done |  |  |  | RINALDI | New Link | New Link 2+0_Ant MW 0.3 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | L1 Approved | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-TJB-0001_SUM-SU-TJB-0187 | L1 Approved |  |  | Doc Resubmit_Bayu | MW
| 283 | 2026-04-23 | S1ID2025042515WBF1-64 | ENT-SU-SBG-0001_ZMDN-4098 | Direktorat Pengelolaan Informasi |  |  | Done |  |  |  | WAHYU WIBISONO | Reroute | Reroute 2+0 | North Sumatra | North Sumatra | 350000275823 | I&C-Seperate MW+0.3-0.6m Antenna 2 | 1000000 |  | Done | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | ENT-SU-SBG-0001_ZMDN-4098 | Not Yet Submit |  |  | Need Cek Nungki / Bayu
| 284 | 2026-04-23 | S1ID2025042515WBF1-62 | SUM-SU-AKK-0062 | PAHING Labuan |  |  | Done |  |  |  | ANGGA WIJAYA | New Site | RAN ONLY | North Sumatra | North Sumatra |  |  | 1350000 |  | Done | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 1350000 | In Progress | Untuk Documen sementara di handle Bayu & Pak Wahyu |  |  |  | SUM-SU-AKK-0062 | OG Rectifikasi | 09/05 Retake data | Angga Wijaya | 09/05 Retake data & setting power 0805 Team Angga Wijaya OG ATP Rektifikasi | RAN
[8 empty] | Done |  |  |  | ANGGA WIJAYA |  |  |  |  | 350001003161 | XLSmart_RRU installation/expansion(RRU Qty(4-6)) |  | 150000 |  | Outbound Done | Not Yet Submit | [12 empty] | 0 | 0 | 0 | 0 | In Progress
[12 empty] | ANGGA WIJAYA |  |  |  |  | 350001003171 | XLSmart_RF Antenna installation(Antenna Qty(1-3)) |  | 150000 |  | N/A | N/A | [12 empty] | 0 | 0 | 0 | 0 | In Progress
[12 empty] | ANGGA WIJAYA |  |  |  |  | 350001003180 | XLSmart_Wireless site commissioning (on Mobile phone) |  | 150000 |  | N/A | N/A | [12 empty] | 0 | 0 | 0 | 0 | In Progress
[12 empty] | ANGGA WIJAYA |  |  |  |  | 350001003181 | XLSmart_Wireless As built document and ATP |  | 150000 |  | N/A | N/A | [12 empty] | 0 | 0 | 0 | 0 | In Progress
[12 empty] | ANGGA WIJAYA |  |  |  |  | 350001003186 | XLSmart_DBS site board expansion |  | 150000 |  | N/A | N/A | [12 empty] | 0 | 0 | 0 | 0 | In Progress
[12 empty] | ANGGA WIJAYA |  |  |  |  | 350001003191 | XLSmart_Filter installation Qty(1-3) |  | 150000 |  | N/A | N/A | [12 empty] | 0 | 0 | 0 | 0 | In Progress
[12 empty] | ANGGA WIJAYA |  |  |  |  | 350001003197 | XLSmart_GPS installation |  | 150000 |  | N/A | N/A | [12 empty] | 0 | 0 | 0 | 0 | In Progress
[12 empty] | ANGGA WIJAYA |  |  |  |  | 350001003252 | XLSmart_DC Power distribution system installation&commissioning&ATP(DC distribution cabinet) |  | 150000 |  | N/A | N/A | [12 empty] | 0 | 0 | 0 | 0 | In Progress
[12 empty] | ANGGA WIJAYA |  |  |  |  | 350001003253 | XLSmart_Battery _48V Lithium Battery Bank(1～2)_Installation |  | 150000 |  | N/A | N/A | [12 empty] | 0 | 0 | 0 | 0 | In Progress
| 285 | 2026-05-02 | Waiting Release | SUM-SU-STB-1314_SUM-SU-STB-1315 | Kodam Atas Bukit Mas_Besitang | 2026-05-04 |  | 2026-05-05 |  |  |  | WAHYU WIBISONO | Survey | MW LOS survey | North Sumatra | North Sumatra | 350000190099 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Waiting Closed ZTE | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress |  |  |  |  | SUM-SU-STB-1314_SUM-SU-STB-1315 | Waiting Closed ZTE |  |  | Summary OK | Survey
| 286 | 2026-05-02 | Waiting Release | SUM-SU-SBG-2228_SUM-SU-SBG-1184 | Binjohara-uruk_Saragih | 2026-05-06 |  | 2026-05-07 |  | Change FE due NE space propos available di bawah existing & critical los |  | RICARDO SINAGA | Survey | MW LOS survey | North Sumatra | North Sumatra | 350000190099 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Done | N/A | Rejected | [12 empty] | 0 | 0 | 0 | 1000000 | In Progress | Change FE due NE space propos available di bawah existing & critical los |  |  |  | SUM-SU-SBG-2228_SUM-SU-SBG-1184 | Change FE |  |  | Change FE due NE space propos available di bawah existing & critical los | Survey
| 287 | 2026-05-05 | Waiting Release | ZMDN-4795_NMDN-0756 |  | 2026-05-06 | [5 empty] | WAHYU WIBISONO | Dismantle MW Keep | Dismantle Ant 0.6m | North Sumatra | North Sumatra | 350000275865 | Dismantling&Simple Packing: MW+0.3-0.6m Antenna 2 | 1000000 |  | Not yet start | Not yet start | Not yet start | [12 empty] | 0 | 0 | 0 | 0 |  | Team On site (Wahyu) Block access warga ke TBG ada yg belum di selesaikan ( Kontrak lahan,perbaikan jalan . penerangan di area tower dll ) |  |  |  | ZMDN-4795_NMDN-0756 | Block Access |  |  | Team On site (Wahyu) Block access warga ke TBG ada yg belum di selesaikan ( Kontrak lahan,perbaikan jalan . penerangan di area tower dll )
| 288 | 2026-05-05 | Waiting Release | SUM-SU-SDK-1223_SUM-SU-SDK-1234 |  | 2026-05-07 |  | 2026-05-07 |  |  |  |  | Dismantle MW Keep | Dismantle Ant 1.2m | North Sumatra | North Sumatra | 350000190026 | Dismantling&Simple Packing: MW+0.7-12m Antenna 2 | 1000000 |  | Done | NY Inbound | Not yet start | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | SUM-SU-SDK-1223_SUM-SU-SDK-1234 | NY Inbound |  |  | Done Dismantle
| 289 | 2026-05-07 | Waiting Release | SUM-AC-STR-0214_SUM-AC-TKN-0210 |  | 2026-05-09 | [6 empty] | Swap Upgrade | Swap Upgrade 4+0_11G_SRU2_4+0 XPIC_1.2_1.2 | Nanggroe Aceh | North Sumatra | 350000190008 | I&C-Seperate MW+0.7-1.2m Antenna (SD)4 | 1000000 |  | Not yet start | Not yet start | Not yet start | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | SUM-AC-STR-0214_SUM-AC-TKN-0210
| 290 | 2026-05-07 | Waiting Release | SUM-AC-STR-0215_SUM-AC-STR-0214 |  | 2026-05-10 | [6 empty] | Swap Upgrade | Swap Upgrade 2+0_13G_SRU2_2+0 XPIC_0.9_0.9 | Nanggroe Aceh | North Sumatra | 350000190003 | I&C-Seperate MW+0.7-1.2m Antenna 2 | 1000000 |  | Not yet start | Not yet start | Not yet start | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | SUM-AC-STR-0215_SUM-AC-STR-0214 | Team On Site | 10/05 MOS | Randi
| 291 | 2026-05-07 | Waiting Release | SUM-SU-GNT-1059_SUM-SU-GNT-1058 |  | 2026-05-10 | [6 empty] | Survey |  |  |  | 350000190099 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Not Yet Start | N/A | Not Yet Start | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | SUM-SU-GNT-1059_SUM-SU-GNT-1058 | Permit Request |  |  | Permit Request | Survey
| 292 | 2026-05-07 | Waiting Release | SUM-SU-AKK-2434_SUM-SU-AKK-1681 |  | 2026-05-10 | [6 empty] | Survey |  |  |  | 350000190099 | MW Technical site survey&Design&LOS Survey | 1000000 |  | Not Yet Start | N/A | Not Yet Start | [12 empty] | 0 | 0 | 0 | 0 | [5 empty] | SUM-SU-AKK-2434_SUM-SU-AKK-1681 | Team On Site | 10/05 Survey TSSR | Wahyu |  | Survey
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
[36 empty] | 0 | 0 | 0 | 0
Note on E2: user: NACH_0010_NACH_0008
Note on E3: user: NACH_0034_NACH_0008
Note on E4: user: NACH_0044_NACH_0043
Note on E5: user: NACH_0053_NACH_0055
Note on E6: user: NACH_0059_NACH_0009
Note on E7: user: NACH_0071_NACH_0061
Note on E8: user: NACH_0124_NACH_0003
Note on E9: user: NACH_0022_NACH_0135
Note on E54: user: SUM-SU-AKK-1527_SUM-SU-AKK-1137
Note on E55: user: SUM-SU-AKK-2412_SUM-SU-AKK-1137
Note on E59: user: ZMDN_4720_NMDN_0167
Note on E60: user: SUM-SU-KPI-2426_SUM-SU-KPI-1163
Note on E62: user: NMDN_0809_NMDN_0180
Note on E63: user: NMDN_0854_NMDN_0086
Note on E73: user: NMDN_0959_ZMDN_4051
Note on E77: user: NMDN_0119_NMDN_0167
Note on E87: user: NMDN_0882_NMDN_0167
Note on E88: user: ZMDN_4664_NMDN_0058
Note on E108: user: SUM-SU-AKK-1116_SUM-SU-KIS-0147
Note on E125: user: ZMDN_4595_ZMDN_5408
Note on E126: user: SUM-SU-KIS-2227_SUM-SU-KIS-0159
Note on E128: user: SUM-SU-AKK-2253_SUM-SU-AKK-0001
Note on E145: user: SUM-SU-AKK-1537_SUM-SU-AKK-1137
Note on E153: user: ZMDN_5322_NMDN_0110
Note on E156: user: ZMDN_4836_NMDN_0155
Note on E172: user: ZMDN_4618_NMDN_0726
Note on E173: user: ZMDN_5346_NMDN_0103
Note on E179: user: SUM-SU-SRH-1266_SUM-SU-PMS-0962
Note on E194: user: ZMDN_4999_NMDN_0100
Note on E195: user: ZMDN_4654_ZMDN_4876
Note on E196: user: ZMDN_5414_NMDN_0985
Note on E197: user: ZMDN_4697_ZMDN_4178
Note on E198: user: NMDN_0402_NMDN_0275
Note on E213: user: NMDN_0828_NMDN_0102
Note on E214: user: NMDN_0746_NMDN_0322
Note on E215: user: ZMDN_4715_ZMDN_4559
Note on E216: user: ZMDN_5327_NMDN_0240
Note on E217: user: ZMDN_4907_NMDN_0265
Note on E218: user: NMDN_0156_ZMDN_4183
Note on E221: user: SUM-AC-BIR-0593_SUM-AC-BIR-0004
Note on E222: user: SUM-AC-BIR-0011_SUM-AC-BIR-0010
Note on E223: user: NMDN_0517_SSBG0002 site id reoute dismantlenya SUM-SU-PSP-8121_SUM-SU-PSP-1217
Note on E224: user: SUM-SU-PYB-1076_SUM-SU-PYB-1081
Note on E229: user: SUM-SU-SBG-1188_SUM-SU-SBG-1187
Note on E233: user: NMDN_0097_NMDN_0238
Note on E262: user: SUM-SU-TRT-2015_SUM-SU-TRT-2008
Note on E263: user: NMDN_0802_ZMDN_4200
Note on E265: user: SUM-SU-PSP-1046_SUM-SU-PSP-1023
Note on E270: user: NMDN_0703_NMDN_0225
Note on E272: user: ZMDN_4045_ZMDN_5288
Note on E317: user: SUM-SU-SRH-2086_SUM-SU-SRH-1947
Note on E318: user: ZMDN_5341_NMDN_0878